## Quotation BOQ
SIX NINE CONSTRUCTION (PVT) LTD
Client: Eastern Highlands Trust / Strickland Lodge
Project: Strickland Lodge Motel - Budgetary Quote
Quotation ID: SNC-STRICKLAND-QT-2026-001 ¦ Revision: 1
Description | Unit | Quantity | Rate | Total
Site establishment and rain protection | item | 1 | 9500 | 0
Clearing, levels and cart-away | m2 | 420 | 9.5 | 0
Substructure and DPM | m2 | 316 | 122 | 0
Ground slab and screed | m2 | 316 | 68 | 0
Masonry walls and partitions | m2 | 560 | 78 | 0
RC columns, beams and lintels | item | 1 | 24500 | 0
Roof structure and coverings | m2 | 380 | 105 | 0
Plaster, skim and paint | m2 | 1120 | 19.5 | 0
Ceilings and cornices | m2 | 316 | 37 | 0
Floor finishes | m2 | 316 | 38 | 0
Wet-area tiling | m2 | 205 | 46 | 0
Doors and ironmongery | no | 24 | 420 | 0
Windows, glazing and bars | no | 22 | 365 | 0
Plumbing and sanitary works | item | 1 | 33500 | 0
Electrical installation | m2 | 316 | 58 | 0
Cupboards, kitchens and joinery | item | 1 | 28500 | 0
Verandahs and external concrete | m2 | 90 | 72 | 0
Stormwater and erosion control | item | 1 | 14500 | 0
Clean, snagging and handover | item | 1 | 6500 | 0
|  |  | Direct Costs: | 362498
|  |  | Preliminaries: | 28500
|  |  | Overheads: | 39099.8
|  |  | Contingency: | 48874.75
|  |  | Profit Margin: | 70379.64
|  |  | Provisional Sums: | 42000
|  |  | Discounts: | 0
|  |  | ZIMRA VAT: | 88702.83
|  |  | GRAND TOTAL: | 680055.02
Assumptions:
- Budgetary pricing only: derived from one A3 floor-plan PDF with no structural, MEP, elevation, finish, soil, survey, or specification pack.
- Pricing is in USD and assumes October to mid-March Zimbabwe rainy-season work, including productivity loss, protection, wet-weather access, stormwater diversion, and programme risk.
- Measured allowance assumes approximately 316 m2 enclosed floor area and approximately 380 m2 roof/covered envelope, subject to CAD/BIM or IFC remeasurement.
- Rates assume conventional masonry construction, reinforced concrete substructure and slab, standard lodge-grade finishes, and normal day-shift labour.
- No client budget was provided; pricing is cost-plus with overhead, rainy-season contingency, provisional sums, and profit separated for audit.
- Final tender must be revised after site visit, soil confirmation, finish schedule, door/window schedule, sanitary schedule, electrical layout, drainage design, and supplier quotations.
Exclusions:
- Land, statutory approvals, professional fees, utility connection fees, permits, levies, and authority charges.
- Abnormal ground, rock excavation, exceptional dewatering, contaminated material, retaining walls, major earthworks, and off-site roadworks.
- Furniture, loose appliances, curtains, linen, signage, landscaping, borehole/water storage, solar/PV, generator, air-conditioning, CCTV, Wi-Fi, and specialist lodge equipment.
- Price escalation, foreign-exchange movement, customs/duty shocks, and material price changes beyond quote validity.
- Any scope not visible or inferable from the single floor-plan drawing.
Audit Trail Hash (Pricing Integrity Key): | d506e4c7f33d25ff4a2405354f478263ed3ae14ff866c7a3fac2c2aaf7b8de2b