## OUTPUT
ESTIMATING DATA
GROUND WORKS
A. SITE CLEARANCE
1,Clear site of all vegetation |  |  |  |  | 1 Lab |  | 20m2/day
B. EXCAVATIONS
1, Normal pickable ground
a) Trenches etc not exceeding 1m deep |  |  |  |  | 1 Lab |  | 2m3/day
Ditto 1-2m deep |  |  |  |  | 1 Lab |  | 1.5m3/day
Ditto 2-3m deep |  |  |  |  | 1 Lab |  | 1m3/day
b) Bases etc not exceeding 1m deep |  |  |  |  | 1 Lab |  | 1.75m3/day
Ditto 1-2m deep |  |  |  |  | 1 Lab |  | 1.20m3/day
Ditto 2-3m deep |  |  |  |  | 1 Lab |  | 0.75m3/day
c) Reduce levels n.e. 1m deep |  |  |  |  | 1 Lab |  | 2.20m3/day
2, Hard pickable ground
As above, but +250% |  |  |  |  | 1 Lab |  | 0.4
3, Rock excavation
As above, but +1200% |  |  |  |  | 1 Lab
C. DISPOSALS
a) Backfilling to trenches and bases |  |  |  |  | 1 Lab |  | 2.5m3/day
b) Loose fill under floor |  |  |  |  | 1 Lab |  | 3.0m3/day
c) Ram fill under floors |  |  |  |  | 1 Lab |  | 2.0m3/day
d) Compacting |  |  |  |  | 1 Lab |  | 35m2/day
e) Load for disposal |  |  |  |  | 1 Lab |  | 1.5m3/day
BRICKWORK AND BLOCKWORK
NB
Adjustments must be made for high standard requirements
All data based on gang of 1 Bricklayer + 2 Assistants
Scaffolding not included
BRICKWORK
Common brickwork:
In foundations,
|  |  | Half brick thick |  |  |  | 375/day
|  |  | One brick thick |  |  |  | 400/day
|  |  | One and half brick thick |  |  |  | 425/day
In superstructure up to 2 storeys,
|  |  | Half brick thick |  |  |  | 350/day
|  |  | One brick thick |  |  |  | 380/day
|  |  | One and half brick thick |  |  |  | 400/day
ESTIMATING DATA
BRICKWORK AND BLOCKWORK
Facing brickwork:
In foundations,
|  |  | Half brick thick |  |  |  | 325/day
|  |  | One brick thick |  |  |  | 340/day
In superstructure up to 2 storeys,
|  |  | Half brick thick |  |  |  | 300/day
|  |  | One brick thick |  |  |  | 325/day
Composite brickwork ( faced on side )
In foundations,
|  |  | One brick thick |  |  |  | 350/day
In superstructure up to 2 storeys,
|  |  | One brick thick |  |  |  | 330/day | 520
Mortar
Mixing by hand | [6 empty] | 8hrs/m3
BLOCKWORK
115mm blockwork:
In foundations | [6 empty] | 180/day
In superstructure | [6 empty] | 150/day
230mm blockwork:
In foundations | [6 empty] | 150/day
In superstructure | [6 empty] | 120/day
SUNDRIES
Beam filling | [6 empty] | 3m/hr/skin
Rough cutting | [6 empty] | 2.5hrs/m2
Cutting pipe chases | [6 empty] | 1.5hrs/m
Copings | [6 empty] | 0.75hrs/m |  |  | 6.643
Fair cuttings | [6 empty] | 1hr/m
Cut small holes | [6 empty] | 1hr/skin
Cut large holes | [6 empty] | 2hrs/skin
Fix door and window frames | [6 empty] | 0.8hrs/m2
Unload and stack | [6 empty] | 3 lab hrs/1000
Painting around frames | [6 empty] | 3hrs/m
Plastering |  |  |  |  | 1+2 |  | 8.4m2/day
MORTAR MIX (per m3)
Mix |  |  |  |  | Cement (50kg) |  | Pit Sand (m3)
3;1 |  |  |  |  | 10.6 |  | 1.3
4;1 |  |  |  |  | 8.9 |  | 1.4
5;1 |  |  |  |  | 7.5 |  | 1.5
6;1 |  |  |  |  | 6.5 |  | 1.6
7;1 |  |  |  |  | 6.2 |  | 1.7
8;1 |  |  |  |  | 5.4 |  | 1.7
Note: Pit sand - Allow 15% bulk factor
ESTIMATING DATA
BRICKWORK
1.Mortar required per m2 of walling:
a. 75mm brick on edge | [6 empty] | 0.02m3 |  | cement | 0.212
b. Half brickwall | [6 empty] | 0.028m3 |  | psand | 0.026
c. One brickwall | [6 empty] | 0.06m3
d. One and half brickwall | [6 empty] | 0.096m3
e. 230 x 230mm clay block wall | [6 empty] | 0.018m3
f. 230 x 150mm ditto | [6 empty] | 0.023m3
2.Brick per m2 of walling (exclude waste) | [5 empty] | Commons | Facings |  |  | 13.3333
a. 75mm brick on edge | [5 empty] | 35 | *
b. Half brickwall | [5 empty] | 52 | *
c. One brickwall | [5 empty] | 104 | * |  |  |  | 266.6667
|  | Based on one brickwall | [8 empty] | 0.00375
d. English bond | [5 empty] | 26 | 78
e. English garden wall bond | [5 empty] | 39 | 65
f. Colonial bond | [5 empty] | 42 | 62
g. Flemish bond | [5 empty] | 39 | 65
h. Mass brickwork per m3 | [5 empty] | 455 | *
3.MORTAR TO BLOCKWORK (per m2 of walling)
a. Nominal 600 x 300mm - 108mm walls | [5 empty] | 0.017m3
b. Nominal 450 x 230mm - 108mm walls | [5 empty] | 0.023m3
|  | - 150mm walls |  |  |  | 0.031m3
|  | - 230mm walls |  |  |  | 0.054m3
Hoop irons 24 ggr = 0.6mm = 6.20kg/m3
CEMENT MORTAR
| MIX | Materials per m3
|  | Cement | Lime-25kg | Sand m3
| 1;1 | 22.4 |  | 0.91
| 1;2 | 10.48 |  | 1.25
| 1;3 | 10.6 |  | 1.38
| 1;4 | 8.9 |  | 1.5
| 1;5 | 7.8 |  | 1.63
| 1;6 | 6.4 |  | 1.69
| 1;7 | 5.9 |  | 1.75
| 1;8 | 5.3 |  | 1.81
| 1;2;9 | 3.6 |  | 1.38
| 1;2;12 | 3 |  | 1.5
| MATERIAL |  |  | CONCRETE GRADE
|  | 10 | 15 | 20 | 25 | 30
| Cement | 5 | 6 | 7 | 9.26 | 10.29
| River sand | 0.8 | 0.8 | 0.74 | 0.7 | 0.65
| 19mm Ag | 0.8 | 0.8 | 0.77 | 0.78 | 0.78
Brick reinforcement per four courses = 2.94m/m2
ESTIMATING DATA
CONCRETING
Labour | [9 empty] | 19.409
A. Mixing concrete |  |  |  | Hourly output |  |  | Lab output/hour
7/5 mixer (200l) |  |  |  | 1.75m3 |  |  | 3/1.7
10/7 mixer (285l) |  |  |  | 3.15m3 |  |  | 3/1.1
14/10 mixer (400l) |  |  |  | 3.85m3 |  |  | 3/0.8
21/14 mixer (600l) |  |  |  | 5.25m3 |  |  | 5/0.9
B. Transport and Place concrete
Mass filling |  |  |  | 2hrs/m3
Foundations,bases,ground beams |  |  |  | 4hrs/m3
Slabs |  |  |  | 6hrs/m3
Blinding |  |  |  | 12hrs/m3
Columns below ground |  |  |  | 8hrs/m3
Columns not exceeding 4m high |  |  |  | 12hrs/m3
Beams not exceeding 4m high |  |  |  | 10hrs/m3
Suspended slabs ditto |  |  |  | 10hrs/m3
Walls |  |  |  | 8hrs/m3
Isolated small areas |  |  |  | 12hrs/m3
Hours to be adjusted accordingly for high level work
Curb concrete |  |  |  | 12m2/hr
Powerfloat finish |  |  |  | 2m2/hr
Steel trowelled |  |  |  | 2m2/hr
Fix expansion joints 150mm wide |  |  |  | 5m/hr
Expansion joint filler |  |  |  | m3/hr
Fix mesh reinforcing |  |  |  | 5m2/hr
FORMWORK
Labour - Shuttering gang based on 1 Carpenter and 2 Assistants
Hard work and strip formwork to: | [6 empty] | Gang hours
Beams | [6 empty] | 0.85/m2
Walls | [6 empty] | 0.75/m2
Columns | [6 empty] | 1.15/m2
Soffits | [6 empty] | 0.80/m2
Narrow widths to edges | [6 empty] | 2.15/m2
PLASTERWORK
Single coat work (walls) - wood float |  |  |  | 1+2 |  |  | 16m2/day
In narrow widths - ditto |  |  |  | 1+2 |  |  | 10m2/day
Single coat work (walls) - steel float |  |  |  | 1+2 |  |  | 14m2/day
In narrow widths - ditto |  |  |  | 1+2 |  |  | 8m2/day
Single coat soffits - wood float |  |  |  | 1+2 |  |  | 12m2/day
Ditto - steel float |  |  |  | 1+2 |  |  | 10m2/day
Two coat work:
1st coat |  |  |  | 1+2 |  |  | 16m2/day
Skim coat |  |  |  | 1+2 |  |  | 23m2/day
ESTIMATING DATA
PLASTERWORK
Floor screeds |  |  |  | 1+2 |  |  | 20m2/day
Narrow widths |  |  |  | 1+2 |  |  | 16m2/day
Precast paving slabs |  |  |  | 1+3 |  |  | 1m2/hr
Wall tiling |  |  |  | 1+1 |  |  | 1m2/hr
Narrow widths |  |  |  | 1+1 |  |  | 0.5m2/hr
GRANO
|  |  | MIX | MATERIALS PER M3
|  |  |  | CEMENT | SAND | CHIPS
|  |  |  | 50kg | M3 | M3
|  |  | 1;3 | 11.4 | * | 1.1
|  |  | 1;1;1.05 | 14.5 | 0.59 | 0.7
|  |  | 1;1;2 | 12 | 0.49 | 0.77
| Rhinosand | [5 empty] | 8m2/sack(25kg)
| Rhinoset | [5 empty] | 20m2/sack
| Rhino bond | [5 empty] | 6m2/sack
| Cemwash | [5 empty] | 12m2/sack/coat
1m3 cment = 30bags
PAINTING
| Paint to ceiling | [5 empty] | 50m2/day
| Paint to walls | [5 empty] | 60m2/day
| Paint to frames | [5 empty] | 50m2/day
| Paint to timber | [5 empty] | 45m2/day
| Paint to small pipes | [5 empty] | 25m/hr/coat
| Paint to large pipes | [5 empty] | 10m/hr/coat
NB. Add 10% to labour figures for turps,brushes etc.
Paint covering capacities
All per 5 litres
| PVA to boards |  |  |  | 5 Litres |  | 1 Litre
| 1st coat |  |  |  | 30m2 |  | 6m2
| 2nd coat |  |  |  | 40m2 |  | 8m2
| 3rd coat |  |  |  | 50m2 |  | 10m2
PVA to plaster
| 1st coat |  |  |  | 40m2 |  | 8m2
| 2nd & 3rd coat |  |  |  | 50m2 |  | 10m2
PVA to blockwork:
| 1st coat |  |  |  | 40m2 |  | 6m2
| 2nd coat |  |  |  | 35m2 |  | 7m2
| 3rd coat |  |  |  | 45m2 |  | 9m2
paint to 230 steel dr frame size 815x2032 =2.03m2
paint to 115 steel dr frame size 815x2032 =1.47m2
ESTIMATING DATA
PAINTING
xs | Primer / Uct / Gloss ct etc |  |  |  | 5 Litres |  | 1 Litre
To steel work:
| 1st coat |  |  |  | 45m2 |  | 9m2
| Subsequent |  |  |  | 50m2 |  | 10m2
To timber:
| 1st coat |  |  |  | 35m2 |  | 7m2
| 2nd coat |  |  |  | 40m2 |  | 8m2
| Subsequent |  |  |  | 50m2 |  | 10m2
REINFORCEMENT
| DIAMETER |  | ROUND |  | PLAIN |  | HIGH
|  |  | MILD |  | SQUARE |  | YIELD
[5 empty] | TWIST |  | DEFORMED
|  |  | ( R ) |  | ( X ) |  | ( Y )
| 6mm |  | 0.222 |  | 0 |  | 0.222
| 6.50mm |  | 0.26 |  | 0.332 |  | 0
| 8mm |  | 0.395 |  | 0.502 |  | 0.395
| 10mm |  | 0.616 |  | 0.784 |  | 0.616
| 12mm |  | 0.887 |  | 1.129 |  | 0.888
| 14mm |  | 1.207 |  | 1.537 |  | 1.21
| 16mm |  | 1.577 |  | 2.008 |  | 1.579
| 20mm |  | 2.464 |  | 3.137 |  | 2.466
| 22mm |  | 2.981 |  | 3.796 |  | 0
| 25mm |  | 3.85 |  | 4.902 |  | 3.854
| 30mm |  | 5.544 |  | 7.059 |  | 0
| 32mm |  | 0 |  | 0 |  | 6.313
| 35mm |  | 0 |  | 9.608 |  | 0
| 40mm |  | 0 |  | 0 |  | 9.869
KGs PER RUNNING METRE
| 1.BASES | [5 empty] | 90kg/m3
| 2.COLUMNS | [5 empty] | 170kg/m3
| 3.WALLS | [5 empty] | 100kg/m3
| 4.SLABS | [5 empty] | 120kg/m3
| 5.BEAMS | [5 empty] | 150kg/m3
FABRIC REINFORCEMENT
| Ref No S245 | [5 empty] | 2.45kg/m2
| Ref No S193 | [5 empty] | 1.93kg/m2
| Ref No S125 | [5 empty] | 1.25kg/m2
Hoop irons 24 ggr = 0.6mm = 6.20 kg/m3
ESTIMATING DATA
BLOCK PRODUCTION DATA
1 Sack cement = 0.034m3
1 Barrow = 0.057m3 ( 2 cu ft )
Block Volumes
( A ) 450 x 220 x 168 hollow = |  |  |  | 0.00666m3/block = 15kg
( B ) 450 x 220 x 103 solid = 0.01070m3/block = 30kg
( C ) 450 x 220 x 216 hollow = 0.00879m3/block = 27kg | [7 empty] | 113.7656
Theoretical Mixes |  |  |  | Mix 1:6 | Mix 1:8 | Mix 1:10 | Mix 1: 12
Cement |  |  |  | 0.034m3 | 0.034m3 | 0.034m3 | 0.034m3
Aggregate |  |  |  | 0.204m3 | 0.272m3 | 0.340m3 | 0.408m3
Practical Equivalents
Cement |  |  |  | 1 sack | 1 sack | 1 sack | 1 sack | 5.4404
Aggregate |  |  |  | 3.5barrws | 4.5barrws | 6 barrows | 7 barrows | 1.057
Dry Volume |  |  |  | 0.234 | 0.291 | 0.376 | 0.433
Waste 5% |  |  |  | 0.012 | 0.015 | 0.019 | 0.022
|  |  |  | 0.222 | 0.276 | 0.357 | 0.411
Mixed Volume |  |  |  | 0.155m3 | 0.193m3 | 0.250m3 | 0.288m3 | 5.1813
Total cost of Blocks (materils only) |  |  |  | 2870
Labour | for 2870 units
SW |  |  |  | 8 | 12 | 1 | 2.5 | 240
WG1 |  |  |  | 8 | 12 | 6 | 1.59 | 915.84
Plant
Concrete Mixer |  |  |  | 4.33 | 0.5 |  | 200 | 433
Subtotal
Maintanance | [5 empty] | 5%
Total Cost all in for production of 2870 blocks
Cost per Block
YIELDS Per SACK
|  |  |  | Mix 1:6 | Mix 1:8 | Mix 1:10 | Mix 1:12
A. |  |  |  | 23 | 29 | 37 | 43
B. |  |  |  | 14 | 18 | 23 | 27
C. |  |  |  | 17 | 22 | 28 | 32
Mortar in filling 230mm hollow blocks 0.013m3/block = 0.124m3/m2
Mortar in filling 115mm hollow blocks 0.007m3/block = 0.067m3/m2
ROOFING
Sheets |  |  |  | 1+4 |  |  | 6sheets/hr
Mitring |  |  |  | 1+1 |  |  | 20sheets/hour
Fix barge and fascia board |  |  |  | 1+2 |  |  | 5m/hr
Fix IBR roof sheeting |  |  |  | 1+4 |  |  | 6m2/hr
Fix tiling battens |  |  |  | 1+2 |  |  | 10m2/3hrs
CARPENTRY
Fix purlins |  |  |  | 1+2 |  |  | 20m/hr
Fix rafters |  |  |  | 1+2 |  |  | 14m/hr
Fix trusses ( 8m ) |  |  |  | 1+4 |  |  | 4No/day
Fix sprockets |  |  |  | 1+2 |  |  | 3m/hr
Fix joists |  |  |  | 1+2 |  |  | 15m/hr
Fix hangers |  |  |  | 1+2 |  |  | 3m/hr
ESTIMATING DATA
CARPENTRY
JOINERY
Fix brandering one way |  |  |  | 1+2 |  |  | 3m2/hr
Fix ceilings |  |  |  | 1+3 |  |  | 2m2/hr
Fix cover strip |  |  |  | 1+2 |  |  | 20m/hr
Fix cornice |  |  |  | 1+2 |  |  | 15m/hr
Fix skirting |  |  |  | 1+2 |  |  | 10m/hr
Fix framing |  |  |  | 1+1 |  |  | 6m/hr
Cut and fix blocked shelving |  |  |  | 1+1 |  |  | 2hrs/sheet
Fix pre-cut shelving |  |  |  | 1+1 |  |  | 6m/hr
Hang doors |  |  |  | 1+2 |  |  | 1No /hr
Plugging |  |  |  | 1+1 |  |  | 8plugs/hr
Screwing |  |  |  | 1+1 |  |  | 20/hr
IRONMONGERY & SUNDRIES
Mortice lock |  |  |  | 1+1 |  |  | 1hr/each
Indicator lock |  |  |  | 1 |  |  | 0.75hrs/each
Shelf brackets |  |  |  | Allow plugs and screws
Curtain track |  |  |  | 1+1 |  |  | 2m/hr
| Rhinoset coverage | [5 empty] | 14m2/25kg bag
| Rhinobond coverage | [5 empty] | 6m2/25kg bag
Turnall Products
| Endurites | [5 empty] | 0.875 wide
| Traffold tiles | [5 empty] | 1.015 wide
| Brickforce ( per 4 courses ) | [5 empty] | 2.94m/m2
ESTIMATING DATA
| Wheelbarrow | [5 empty] | 0.057m3
| Sack cement | [5 empty] | 0.034m3
Grout
|  |  | a+b | xcxdx1.7 | kg/m2
axb
where a - length of tile
b - width of tile
c - thickness of tile
d - average joint width
Note on I339: wchikwanyanga: 1m3 of mortar yields this

## EST CONSTANTS
CONVERSIONS FOR PREPARING SCHEDULE OF MATERIALS
WET TRADES
SUBSTRUCTURE
Concrete
| Grade 10-20 | m3 | 1
7;;] |  |  | sand | 0.7875
|  |  | cement | 4.4625
|  |  | stone | 0.8505
| Grade 20-20 | m3 | 1
|  |  | sand | 0.714
|  |  | cement | 7.14
|  |  | stone | 0.882
| Grade 25-20 | m3 | 1
|  |  | sand | 0.714
|  |  | cement | 5.985
|  |  | stone | 0.882
| Grade 30-20 | m3 | 1
|  |  | sand | 0.7035
|  |  | cement | 8.8725
|  |  | stone | 0.903
| Grade 30-40 | m3 | 1
|  |  | sand | 0.714
|  |  | cement | 6.51
|  |  | stone | 0.903
| Grade 40-20 | m3 | 1
|  |  | sand | 0.6195
|  |  | cement | 7.56
|  |  | stone | 0.9135
Polythene sheeting
|  | m2 | 1
|  |  | m | 0.66667
Mesh fabric reinforcement Ref S193
|  | m2 | 1
|  |  | sheets | 0.069444
Hardcore
|  | m3 | 1 | 1
Sand blinding
|  | m3 | 1 | 1
Termite treatment
|  | m2 | 10
|  |  | litres | 1.087
Half brick wall
|  | m2 | 102
|  |  | commons | 5569.2
|  |  | pit sand | 2.5276
|  |  | cement | 13.9337
One brick wall
|  | m2 | 82
|  |  | commons | 9040.5
|  |  | pit sand | 5.1574
|  |  | cement | 28.5249
Piers
|  | m3 | 0.11
|  |  | commons | 52.899
|  |  | pit sand | 0.035493
|  |  | cement | 0.19625
Face Brick Wall
|  | m2 | 1
|  |  | facings | 55.65
|  |  | pit sand | 0.02478
|  |  | cement | 0.13661
Brick-on-edge
|  | m2 | 1
|  |  | bricks | 38.38
|  |  | pit sand | 0.01785
|  |  | cement | 0.02457
Damp proof course for half brick wall
|  | m | 1
|  |  | roll | 0.045455
Damp proof course for one brick wall
|  | m | 1
|  |  | roll | 0.045455
Ref C1 for half brick wall
|  | m | 100
|  |  | roll | 5
Ref C2 for one brick wall
|  | m | 221
|  |  | roll | 11.05
Steel bar reinforcement
|  | m3 | 221
|  |  | kg | 26520
10mm Expansion joint.
|  | m2 | 0
|  |  | sheets | 0
3 ply bituminous felt sheeting
|  | m2 | 1
|  |  | sheets | 1.0417
Thioflex sealant.
|  | m | 2
|  |  | tubes | 0.33333
Woodfloat plaster
|  | m2 | 1
|  |  | pit sand | 0.0231
|  |  | cement | 0.22176
|  |  | undercoat | 0.076087
|  |  | EPVA | 0.22826
| SUPERSTRUCTURE |  |  | cement-0.33m3
Concrete
| Grade 10-20 | m3 | 14
|  |  | sand | 11.025
|  |  | cement | 77.175
|  |  | stone | 11.907
18
| Grade 20-20 | m3 | 1
|  |  | sand | 0.777
|  |  | cement | 7.14
|  |  | stone | 0.8085
| Grade 25-20 | m3 | 18
|  |  | sand | 12.852
|  |  | cement | 139.86
|  |  | stone | 15.876
| Grade 30-20 | m3 | 13
|  |  | sand | 9.4185
|  |  | cement | 109.2
|  |  | stone | 11.739
| Grade 30-40 | m3 | 1
|  |  | sand | 0.714
|  |  | cement | 6.51
|  |  | stone | 0.903
| Grade 40-20 | m3 | 1
|  |  | sand | 0.6195
|  |  | cement | 7.56
|  |  | stone | 0.9135
Screeds
|  | m2 | 1
|  |  | river sand | 0.0462
|  |  | cement | 0.44352
Half brick wall
|  | m2 | 1
|  |  | commons | 54.6
|  |  | pit sand | 0.02478
|  |  | cement | 0.168
One brick wall
|  | m2 | 290
|  |  | commons | 31972.5
|  |  | pit sand | 18.2396
|  |  | cement | 100.8809
| Face Brick Wall m2 |  | 1
|  |  | facings | 55.65
|  |  | pit sand | 0.02478
|  |  | cement | 0.13661
Piers
|  | m3 | 1
|  |  | commons | 411.6
|  |  | pit sand | 0.32267
|  |  | cement | 1.7841
Brick-on-edge
|  | m2 | 1
|  |  | bricks | 38.38
|  |  | pit sand | 0.01785
|  |  | cement | 0.02457
150 mm Block wall
|  | m2 | 1
|  |  | blocks | 10.3635
|  |  | pit sand | 0.0315
|  |  | cement | 0.2205
Damp proof course for half brick wall
|  | m | 1
|  |  | roll | 0.045455
Damp proof course for one brick wall
|  | m | 1
|  |  | roll | 0.045455
Ref C1 for half brick wall
|  | m | 1
|  |  | roll | 0.05
Ref C2 for one brick wall
|  | m | 1
|  |  | roll | 0.05
Mesh fabric reinforcement 6*2.4m)
|  | m2 | 1
|  |  | sheets | 0.069444
Steel bar reinforcement
|  | m3 | 0
|  |  | kg | 0
150 x 150 mm White glazed wall tiles
|  | m2 | 1
|  |  | tiles | 52.5
|  |  | Grout | 0.1 | 5kg
|  |  | tile addhesive | 0.16667 | 20kg
Render and set to walls
|  | m2 | 1
|  |  | pit sand | 0.0252
|  |  | cement | 0.18144
|  |  | rhinoset | 0.07
|  |  | undercoat | 0.13125
|  |  | IPVA | 0.22826
Woodfloat plaster
|  | m2 | 220
|  |  | pit sand | 5.082
|  |  | cement | 48.7872
|  |  | undercoat | 28.875
|  |  | EPVA | 50.2174
Redecoration to existing int. walls
|  | m2 | 872
|  |  | pit sand | 0
|  |  | cement | 0
|  |  | rhinoset | 0
|  |  | undercoat | 66.3478
|  |  | IPVA | 199.0435
Redecoration to existing Ext. walls
|  | m2 | 1
|  |  | pit sand | 0
|  |  | cement | 0
|  |  | undercoat | 0.076087
|  |  | EPVA | 0.22826
Plasterboard ceilings redecor
|  | m2 | 1
|  |  | Rhinobond | 0
|  | Sheets | 2100*1200 | 0
|  |  | ceiling white | 0.18453
|  |  | clout nails | 0
|  |  | brandering | 0
Plasterboard ceilings
|  | m2 | 74
|  |  | Rhinobond | 15.54
|  | Sheets | 3600*1800 | 12.693
|  |  | ceiling white | 13.6555
|  |  | clout nails | 777
|  |  | brandering | 370
|  |  | covebond | 3.885
ROOF COVERINGS
Concrete roof tiles
|  | m2 | 1
|  |  | no. | 14.7
Cill ( quarry tiles)
|  | m | 1
|  |  | no. | 46.6667
|  |  | pit sand | 0.062895
|  |  | cement | 0.34786
Roof nails
|  | m2 | 1
|  |  | kg | 0.1
| Battens | m2 | 1
|  |  | m | 3.2
Skirting
|  | m | 2
|  | varnish | L | 0.35117
Pelmets
|  | m | 1
|  | varnish | L | 0.17559
300 x 300 Vinyl tiles
|  | m2 | 1
|  |  | tiles | 11.6667
|  |  | tylon | 0.1
|  |  | tile adhesive | 0.16667
150 x 150 Quarry floor tiles
|  | m2 | 1
|  |  | tiles | 46.6667
Wall plate
|  | m | 1
| galvanised hoop iron ties |  |  | 1.4
|  | carbolineum |  | 0.10375
Painting to metal
|  | m2 | 30
|  |  | undercoat | 2.6338
|  |  | metal primer | 2.6338
|  |  | high gloss | 5.2676
Painting to wood
|  | m2 | 50
|  | undercoat |  | 4.3896
|  | wood primer |  | 4.3896
|  | high gloss |  | 8.7793
Note on J231: MACO Builders:
Note on E246: MACO Builders:
Note on F246: MACO Builders:

## FNDTNS
ONE BRICK WALL |  | note - brickforce is every 3 courses and includes 10% waste
bricks do not include waste
mortar |  | cement | pit sand | bricks | brickforce
mix | area | bags | m3 | no. | rolls
1:1 |  | 0 | 0 | 0 | 0
1:2 |  | 0 | 0 | 0 | 0
1:3 |  | 0 | 0 | 0 | 0
1:4 | 100 | 38.7 | 6.75 | 11000 | 19.6
1:5 |  | 0 | 0 | 0 | 0
HALF BRICK WALL
mortar |  | cement | pit sand | bricks | brickforce
mix | area | bags | m3 | no. | rolls
1:1 |  | 0 | 0 | 0 | 0
1:2 |  | 0 | 0 | 0 | 0
1:3 |  | 0 | 0 | 0 | 0
1:4 | 14 | 2.408 | 0.42 | 840 | 2.744
1:5 |  | 0 | 0 | 0 | 0
|  | cement | pit sand | bricks
TOTAL |  | 41.108 | 7.17 | 11840
|  | bags | m3 | no.
CONCRETE WORKS
|  | cement | sand | 19mm ag
grade | volume | bags | m3 | no.
10 | 0.72 | 3.6 | 0.576 | 0.576
15 | 1 | 6 | 0.8 | 0.8
1
20 | 1 | 7 | 0.74 | 0.77
25 | 1 | 9.26 | 0.7 | 0.78
30 | 1 | 10.29 | 0.65 | 0.78
ratio
1:3:6 | 1 | 4.3 | 0.55 | 0.88
1:2:4 | 1 | 6.08 | 0.53 | 0.84
|  | cement | sand | 19mm ag
TOTAL |  | 46.53 | 4.546 | 5.426
|  | bags | m3 | m3

## BWRK
ONE BRICK WALL |  | note - brickforce is every 4 courses and includes 10% waste
note-Waste included on bricks
mortar |  | cement | pit sand | bricks | brickforce
mix | area | bags | m3 | no. | rolls
1:1 | 0 | 0 | 0 | 0 | 0
1:2 | 0 | 0 | 0 | 0 | 0
1:3 |  | 0 | 0 | 0 | 0
1:4 | 480 | 185.76 | 32.4 | 52800 | 77.616
1:5 | 10 | 3.51 | 0.7335 | 1200 | 1.47
HALF BRICK WALL
mortar |  | cement | pit sand | bricks | brickforce
mix | area | bags | m3 | no. | rolls
1:1 | 0 | 0 | 0 | 0 | 0
1:2 | 0 | 0 | 0 | 0 | 0
1:3 |  | 0 | 0 | 0 | 0
1:4 | 100 | 17.2 | 3 | 6000 | 16.17
1:5 |  | 0 | 0 | 0 | 0
|  | cement | pit sand | bricks | 230mm Brickforce |  | 115mm brickforce
TOTAL |  | 206.47 | 36.1335 | 60000 | 1581.72 | 79.086 | 323.4 | 16.17
|  | bags | m3 | no. | m | rolls | m | rolls

## PLASTER
PLASTER |  | 20mm Plaster
mortar |  |  | cement | pit sand
mix | area |  | bags | m3
1:1 | 0 |  | 0 | 0
1:2 | 0 |  | 0 | 0
1:3 |  |  | 0 | 0
1:4 |  |  | 0 | 0
1:5 | 102 |  | 15.912 | 3.3252
1:6 | 1 |  | 0.128 | 0.0338
PLASTER |  | 10mm Plaster
mortar |  |  | cement | pit sand
mix | area |  | bags | m3
1:1 | 0 |  | 0 | 0
1:2 | 0 |  | 0 | 0
1:3 | 10 |  | 1.04 | 0.138
1:4 | 130 |  | 11.18 | 1.95
1:5 | 1 |  | 0.078 | 0.0163
1:6 | 0 |  | 0 | 0
|  |  | cement | pit sand
TOTAL |  |  | 28.338 | 5.4633
|  |  | bags | m3

## SCREED
SCREED |  | 40mm Screed
mortar |  |  | cement | river sand
mix | area |  | bags | m3
1:1 | 0 |  | 0 | 0
1:2 | 0 |  | 0 | 0
1:3 | 1342 |  | 558.272 | 74.0784
1:4 | 180 |  | 61.92 | 10.8
1:5 |  |  | 0 | 0
1:6 | 0 |  | 0 | 0
SCREED |  | 50mm Screed
mortar |  |  | cement | river sand
mix | area |  | bags | m3
1:1 | 0 |  | 0 | 0
1:2 | 0 |  | 0 | 0
1:3 | 0 |  | 0 | 0
1:4 | 580 |  | 249.4 | 43.5
1:5 | 18.3 |  | 7.137 | 1.4914
1:6 | 0 |  | 0 | 0
|  |  | cement | pit sand | 24
TOTAL |  |  | 876.729 | 129.8698 | 4.8
|  |  | bags | m3

## PAINTING
PVA Paint to Boards |  |  | Unit = 5 litre tins
Area | 1st Coat | 2nd Coat | 3rd Coat | Total
1 | 0.033333 | 0.025 | 0.02 | 0.078333 | no of 5 ltr tins
PVA Paint to Plaster |  |  | Unit = 5 litre tins
Area | 1st Coat | 2nd Coat | 3rd Coat | Total
122 | 3.05 | 2.44 | 2.44 | 7.93 | no of 5 ltr tins
PVA Paint to Blockwork |  |  | Unit = 5 litre tins
Area | 1st Coat | 2nd Coat | 3rd Coat | Total
| 0 | 0 | 0 | 0 | no of 5 ltr tins
PVA Paint to Steelwork |  |  | Unit = 5 litre tins
Area | 1st Coat | 2nd Coat | 3rd Coat | Total
1 | 0.022222 | 0.02 | 0.022222 | 0.064444 | no of 5 ltr tins
PVA Paint to Timber |  |  | Unit = 5 litre tins
Area | 1st Coat | 2nd Coat | 3rd Coat | Total
1 | 0.028571 | 0.025 | 0.02 | 0.073571 | no of 5 ltr tins
|  |  | 4.925 | 0.087222
3.1341

## Girth & Opps
Girth Collection
230mm External wall |  | 230mm Verand | 115mm External wall | 230mm Internal wall | 115mm Internal wall |  |  | Deductions
[7 empty] | On 230 Ver | On 230 Ex | On 230 In | On 115 Ex | On 115 In
43.96 |  | 8.46 | 0 | 0 | 49
0 |  | 0 | 0 | 0 | 0 |  | 11.71 | 21.28 | 0 | 0 | 16.9 | m2
0 |  | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0
0 |  | 0 | 0 | 0 | 0 |  |  | Height of Brick work
0 |  |  | 0 | 0 | 0 |  | On 230 Ve | On 230 Ex | On 230 In | On 115 Ex | On 115 In
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0 |  | 2.72 | 2.72 | 2.72 | 2.72 | 2.72
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0 |  |  | Area of Brick work
0 |  |  | 0 | 0 | 0 |  | On 230 Veran | On 230 Ex | On 230 In | On 115 Ex | On 115 In
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0 |  | 11.3012 | 98.2912 | 0 | 0 | 116.38
43.96 |  | 8.46 | 0 | 0 | 49
Gross Floor Areas
|  |  |  | Area | Skirting
Ceramic Tiles |  |  |  | 32.45 | 39.94
Granolithic |  |  |  | 13.97 | 14.21
Carpet |  |  |  | 33.42 | 37.85
Vinyl |  |  |  | 18.15 | 34.92
Gross Floor Area ie Total floor area |  |  |  | 97.99 | 318
Roof Construction |  |  | Floor area | Angle Deg | Area of Roof
|  |  | 85 | 12.5 | 85.1166
|  |  | 0 | 17.5 | 0
|  |  | 318 | 30 | 367.1948
|  |  | Total |  | 452.3114
Windows
Window type | No. | Length | Height | Area | Clear | Obscure
E7H | 1 | 1.022 | 0.654 | 0.66839 | 0.66839
E7H | 1 | 1.022 | 0.654 | 0.66839 | 0.66839
D11F | 1 | 2 | 1.248 | 2.496 | 2.496
D11F | 1 | 2 | 1.248 | 2.496 | 2.496
D11F | 1 | 2 | 1.248 | 2.496 | 2.496
D11F | 1 | 2 | 1.248 | 2.496 | 2.496
C4F | 1 | 1.511 | 0.951 | 1.437 | 1.437
E1 | 1 | 0.533 | 0.654 | 0.34858 | 0 | 0.34858
E1 | 1 | 0.533 | 0.654 | 0.34858 | 0 | 0.34858
E1 | 1 | 0.533 | 0.654 | 0.34858 | 0 | 0.34858
E1 | 1 | 0.533 | 0.654 | 0.34858 | 0 | 0.34858
D2FH | 1 | 1.022 | 1.248 | 1.2755 | 1.2755
W8 | 6 | 0.508 | 2.1 | 6.4008 | 6.4008
Total |  | 15.217 | 13.215 | 21.8283 | 20.434 | 1.3943

## Subie Valuation
MACO BUILDERS
Address : 18 Browning road Malindela Bulawayo.
Phone : (09) 243107-8
Main-Contractor Valuation Account |  |  |  | DATE : | 26/03/2014
CONTRACTOR |  | FUNDED CONSTRUCTION
CONTRACT WORK |  | OFFICE RENOVATIONS
PROJECT |  | ………………………………
SUBCONTRACT PAYMENT ADVICE |  | No. | 1
Preliminary & Generals |  |  |  |  | 540
Value of work done (to date)
Contract sum |  |  |  |  | 28948.96
Additions |  |  |  |  | 1930.23
Variations (tiles in lieu of epoxy)
Generator shed |  |  |  |  | 539.11
TOTAL |  |  |  |  | 31419.19
Less ; 10% Retention |  |  |  |  | 0
31419.19
Variations |  |  |  |  | 0
Materials On /Off Site |  |  |  |  | 0
Certified value of increased costs (Labour) |  |  |  |  | 0
Gross Total Value |  |  |  |  | 31419.19
Less Previous Payments |  |  |  |  | 0
31419.19
Less 10% Witholding tax |  |  |  |  | 3141.919
Net Total Value |  |  |  |  | 28277.271
For Office Use Only
Certified in Certificate No. |  | Applied in Application No.
Prepared by (QS) | …………………………………………. | Date : | ……………………
Sub-Contractor
Checked By | ………………………………………… | Projects Manager |  |  | Accounts
Authorised by | ………………………………………… | General Manager |  |  | Project QS

## Sheet2
WINDOW & DOOR SCHEDULE FOR THE PROPOSED
House for Mr & Mrs Mpofu
ITEM | DESCRIPTION | UNIT | QTY | PRICE | COST
NO
A | STANDARD PRIMED MILD STEEL WINDOW FRAMES
1 | Type ND11F | No. | 8 | 101 | 808
2 | Type NE11 | No. | 1 | 61 | 61
3 | Type NE4 | No. | 2 | 57 | 114
4 | Type NE1 | No. | 1 | 27 | 27
5 | Type NC11F | No. | 1 | 94 | 94
6 | Type ND2F | No. | 2 | 62 | 124
Pressed Steel Door Frame
7 | Frame size 813x 2032 x 115mm | No | 7 | 40 | 280
8 | Frame size 813x 2032 x 230mm | No | 8 | 54 | 432
9 | NDAS | No | 2 | 196 | 392
B | JOINERY AND IRON MONGERY
DOORS
44mm External quality semi solid core flush panel doors
suitable for painting and hung to pressed steel frames
1 | Door size 813x2032mm high | No | 3 | 28.5 | 85.5
44mm Internal quality semi solid core flush panel doors
suitable for painting and hung to pressed steel frames
2 | Door size 813x2032mm high | No | 11 | 54 | 594
3 | 2 Hour Firedoor | No | 1 |  | 0
4 | 3 Lever Mortice locksets | No | 3 | 15 | 45
5 | 2 Lever Mortice locksets | No | 12 | 12.5 | 150
| TOTAL MATERIAL COST |  |  |  | 3206.5
| TOTAL COST |  |  |  | 3206.5

## Sheet3
SCHEDULE OF MATERIALS FOR THE PROPOSED
Additions To Mr. & Mrs N Mabhena's Cottage
ITEM | DESCRIPTION | UNIT | QTY | PRICE | COST
NO
1.0 | SUBSTRUCTURE UP TO DPC LEVEL
1 | PC 15 Cement | Bgs | 23 | 12 | 276
2 | River Sand | m3 | 3 | 40 | 120
3 | Pit Sand | m3 | 1 | 40 | 40
4 | 20mm Concrete stone | m3 | 4 | 50 | 200
5 | Approved industrial bricks | No | 1100 | 0.23 | 253
6 | Black polythene 250 micron | m2 | 22 | 1.35 | 29.7
7 | Ant poison (5L) | No | 1 | 12 | 12
8 | 230 mm Brickforce 22 M | Roll | 2 | 5 | 10
9 | 115 mm Brickforce 22 M | Roll | 1 | 4 | 4
10 | Imported gravel fill under floating slab | m3 | 3 | 30 | 90
1034.7
2.0 | SUPERSTRUCTURE BRICKWORK
1 | PC 15 Cement for brickwork | Bags | 10 | 12 | 120
2 | Pit Sand | m3 | 2 | 40 | 80
3 | Common Bricks | No | 2900 | 0.18 | 522
4 | Air Bricks | Pairs | 6 | 3 | 18
5 | 230 mm Brickforce 20m | Roll | 4 | 5 | 20
6 | 115 mm Brickforce 20 m | Roll | 2 | 4 | 8
7 | 230 DPC 20m | Roll | 1 | 12 | 12
8 | 115 DPC 20m | Roll | 1 | 8 | 8
788
3 | ROOF COVERINGS AND CARPENTRY
Turnall or similar approved asbestos endurite
1 | roofing sheets 3.6m | no. | 8 | 28 | 224
2 | 1.8m | no. | 8 | 13.56 | 108.48
3 | Timber 152*38*6.6m | no. | 3 | 12 | 36
4 | Ridges | pairs | 8 | 28 | 224
5 | Galvanised Flashing (3m*925).4mm | sheets | 2 | 13.63 | 27.26
6 | Asbestos Nails | kg | 1 | 8 | 8
7 | Wire nails | kg | 2 | 3 | 6
633.74
4 | METAL WORK
Pressed Steel Door Frame
1 | Frame size 813x 2032 x 115mm | No | 1 | 46.96 | 46.96
2 | Frame size 813x 2032 x 230mm | No | 1 | 56 | 56
102.96
STANDARD PRIMED MILD STEEL WINDOW FRAMES
3 | Type ND11F | No. | 1 | 101 | 101
4 | Type NC4F | No. | 2 | 74.63 | 149.26
250.26
5 | JOINERY AND IRON MONGERY
DOORS
44mm External quality semi solid core
flush panel doors
1 | Door size 813x2032mm high | No | 1 | 54 | 54
44mm Internal quality semi solid core
flush panel doors
2 | Door size 813x2032mm high | No | 1 | 28.5 | 28.5
IRONMONGERY
The following ironmongery to be fixed to timber
doors and pressed steel frames
"Union" or similar approved lockset
3 | Three lever Union lockset | No | 1 | 15 | 15
4 | Two lever Union lockset | No | 1 | 12.5 | 12.5
5 | Rubber door stop | No. | 2 | 1 | 2
112
6 | PLASTERING & FLOOR SCREEDS & untinted grano
1 | Cement | no. | 22 | 12 | 264
2 | Pitsand | m3 | 2 | 40 | 80
3 | Riversand | m3 | 3 | 40 | 120
NOTE : SCREED IS 1:4 RATIO
464
7 | GLAZING
1 | 3mm thick Clear sheet glass | m2 | 5.26 | 5.2 | 27.352
8 | PLUMBING AND DRAINAGE
SANITARY FITTINGS
5 | 32mm waste pipe | m |  | 1.3 | 0
6 | 32mm*90º inspection bends | no. |  | 0.59 | 0
7 | 32mm rubber s-trape | no. |  | 2.9 | 0
8 | 32mm rubberp-trape | no. |  | 2.9 | 0
13 | 15mm elbows | no. |  | 0.4 | 0
14 | 15mm Copper Tees | no. |  | 0.6 | 0
15 | 15mm Copper straight connectors | no. |  | 0.5 | 0
16 | 22mm Copper Pipes | m |  | 3.5 | 0
17 | 15mm copper pipes | m |  | 3 | 0
18 | Double bowel stainless steel sink | no. |  | 80 | 0

## Sheet4
MR. & MRS MABHENA
Additions to cottage
Supply and fix quote.
Item | Description | Cost
1 | Excavating & building including all
| allied works up to slab level | 1940.89
Building superstructure including
2 | supply & building in all window and door
| frames | 2338.17
3 | Fixing of roof beams, rafters and
| laying asbestos endurite roof sheets | 1156.04
4 | Hanging all doors to appropriate
| openings and fixing the locksets | 226.8
Plastering of walls both externally and
5 | internally also including laying a 40mm
screed and 20mm untinted grano to
| appropriate rooms. | 1051
6 | Glazing with 3mm clear glass to steel
| sashes . | 94.29
| TOTAL COST | 6807.19

## Sheet5
MANSIONS AFRICA
Description | UNIT | QNTY | RATE | AMOUNT
stripping 150mm topsoil around site | m2 | 110 | 7 | 770
Setting out | item |  |  | 200
Excavate foundation trenches | m3 | 35 | 7 | 245
0
Cast the concrete in strip footing foundations | m3 | 13 | 15 | 195
0
230mm brickwork in foundations | m2 | 35 | 20 | 700
0
115mm brickwork in foundations | m2 | 21 | 10 | 210
0
Hardcore, approved non expansive material | m3 | 275 | 25 | 6875
Waterproofing | m2 | 345 | 0.5 | 172.5
Termite treatment | m2 | 345 | 0.2 | 69
Concrete to floor slabs | m3 | 45 | 15 | 675
strike off and curing | m2 | 345 | 0.2 | 69
Total |  |  |  | 10180.5
SUPERSTRUCTURE
Description | UNIT | QNTY | RATE | AMOUNT
230mm common brickwall in internal partitions | m2 | 116 | 20 | 2320
0
230mm common brickwall in toilet area | m2 | 148 | 20 | 2960
230mm common brickwall for the delivery yard area | m2 | 118 | 20 | 2360
115mm common brickwall | m2 | 59 | 10 | 590
Build in frames Including door and window frames | no. | 30 | 4.5 | 135
smooth off-shutter to underside of slab soffit | m2 | 78 | 3 | 234
shuttering of roof slab | m2 | 80 | 8 | 640
fix S125 weld mesh in roof slab | m2 | 78 | 0.6 | 46.8
concreting of roof slab | m3 | 12 | 25 | 300
one coat cement plaster to internal brick walls | m2 | 742 | 5.1 | 3784.2
one coat cement plaster to external walls | m2 |  | 5.1 | 0
0
prepare surfaces and apply paint to internal walls | m2 | 742 | 4.2 | 3116.4
apply paint to internal soffit of roof slab | m2 | 78 | 4.2 | 327.6
prepare surfaces and apply paint to external walls,
soffits and edges of roof slab | m2 |  | 4.2 | 0
prepare surfaces and apply water proofing complete
with silver paint to top of roof slab | m2 | 78 | 8.5 | 663
paint and apply 1u/coat & 2 coats doors including
door frames and window frames. | no. | 17 | 12 | 204
door fixing | no. | 17 | 8.5 | 144.5
Total |  |  |  | 17825.5
ROOFING
0
SOLUSI | UNIT | QNTY | RATE | #VALUE!
0
smooth off-shutter to underside of slab soffit | m2 | 3 |  | 0
0
shuttering of roof slab | m2 | 37.9 | 245146.08 | 9291036.432
0
reinforcement of roof slab | m2 | 25.2 | 143412.96 | 3614006.592
0
fix S125 weld mesh in roof slab | m2 | 37 | 13583.26 | 502580.62
0
concreting of roof slab | m3 | 6.3 | 925575.84 | 5831127.792
0
Concreting of floor slab | m3 | 2 | 925575.84 | 1851151.68
0
one coat cement plaster to internal brick walls | m2 | 84.1 | 71670.62 | 6027499.142
0
one coat cement plaster to external walls | m2 | 62.2 | 71670.62 | 4457912.564
0
prepare surfaces and apply paint to internal walls | m2 | 84.5 | 91302.63 | 7715072.235
0
apply paint to internal soffit of roof slab | m2 | 20.7 | 124858.29 | 2584566.603
0
prepare surfaces and apply paint to external walls, |  |  |  | 0
soffits and edges of roof slab | m2 | 79.8 | 228256.55 | 18214872.69
0
prepare surfaces and apply water proofing complete |  |  |  | 0
with silver paint to top of roof slab | m2 | 37.9 | 280931.13 | 10647289.827
0
paint RLU doors including door frames | no. | 1 | 163876.48 | 163876.48
0
door fixing | no. | 1 | 280931.13 | 280931.13
0
backfilling of bases | m3 | 58.8 | 116330.58 | 6840238.104
0
compaction of bases | m3 | 58.8 | 8309.33 | 488588.604
0
stripping 150mm topsoil around site | m2 | 168 | 14541.32 | 2442941.76
0
spreading inert materials | m3 | 10.5 | 116330.58 | 1221471.09
0
compaction of inert materials over site | m3 | 10.5 | 8309.33 | 87247.965
0
100mm depth of 20mm stone to be rolled over site | m3 | 12 |  | 0
0
stripping 1m outside perimeter fence | m2 | 23 | 14541.32 | 334450.36
0
0
MKOBA | UNIT | QNTY | RATE | #VALUE!
0
concreting generator slab | m3 | 6.3 | 925575.84 | 5831127.792
0
backfilling of bases | m3 | 58.8 | 116330.58 | 6840238.104
0
compaction of bases | m3 | 58.8 | 8309.33 | 488588.604
0
stripping 150mm topsoil around site | m2 | 168 | 16693.7 | 2804541.6
0
spreading inert materials | m3 | 10.5 | 116330.58 | 1221471.09
0
compaction of inert materials over site | m3 | 10.5 | 8309.33 | 87247.965
0
100mm depth of 20mm stone to be rolled over site | m3 | 12 |  | 0
0
stripping 1m outside perimeter fence | m2 | 23 | 14541.32 | 334450.36
0
0
ZIMASCO | UNIT | QNTY | RATE | #VALUE!
0
concreting of generator slab | m3 | 6.3 | 925575.84 | 5831127.792
0
backfilling of bases | m3 | 58.8 | 116330.58 | 6840238.104
0
compaction of bases | m3 | 58.8 | 8309.33 | 488588.604
0
stripping 150mm topsoil around site | m2 | 168 | 16693.7 | 2804541.6
0
spreading inert materials | m3 | 10.5 | 116330.58 | 1221471.09
0
compaction of inert materials over site | m3 | 10.5 | 8309.33 | 87247.965
0
100mm depth of 20mm stone to be rolled over site | m3 | 12 |  | 0
0
stripping 1m outside perimeter fence | m2 | 23 | 14541.32 | 334450.36
0
0
LALAPANSI | UNIT | QNTY | RATE | #VALUE!
0
prepare surfaces and apply paint to internal walls | m2 | 84.5 | 91302.63 | 7715072.235
0
apply paint to internal soffit of roof slab | m2 | 20.7 | 124858.29 | 2584566.603
0
prepare surfaces and apply paint to external walls, |  |  | . | #VALUE!
soffits and edges of roof slab | m2 | 79.8 | 280931.13 | 22418304.174
0
prepare surfaces and apply water proofing complete |  |  |  | 0
with silver paint to top of roof slab | m2 | 37.9 | 228256.55 | 8650923.245
0
paint RLU doors including door frames | no. | 1 | 163876.48 | 163876.48
0
door fixing | no. | 1 | 280931.13 | 280931.13
0
backfilling of bases | m3 | 58.8 | 116330.58 | 6840238.104
0
compaction of bases | m3 | 58.8 | 8309.33 | 488588.604
0
stripping 150mm topsoil around site | m2 | 168 | 14541.32 | 2442941.76
0
spreading inert materials | m3 | 10.5 | 116330.58 | 1221471.09
0
compaction of inert materials over site | m3 | 10.5 | 8309.33 | 87247.965
0
100mm depth of 20mm stone to be rolled over site | m3 | 12 |  | 0
0
stripping 1m outside perimeter fence | m2 | 23 | 14541.32 | 334450.36
0
0
SHANGANI MINE | UNIT | QNTY | RATE | #VALUE!
0
stripping 150mm topsoil around site | m2 | 168 | 16693.7 | 2804541.6
0
spreading inert materials | m3 | 10.5 | 116330.58 | 1221471.09
0
compaction of inert materials over site | m3 | 10.5 | 8309.33 | 87247.965
0
100mm depth of 20mm stone to be rolled over site | m3 | 12 |  | 0
0
stripping 1m outside perimeter fence | m2 | 23 | 14541.32 | 334450.36
0
0
0
0

## Sheet1
The art of construction estimating
1.1 Introduction
Cost is important to all industry. Costs can be divided into two general classes; absolute costs and relative costs. Absolute cost measures the loss in value of assets. Relative cost involves a comparison between the chosen course of action and the course of action that was rejected. This cost of the alternative action - the action not taken - is often called the "opportunity cost".
The accountant is primarily concerned with the absolute cost. However, the forest engineer, the planner, the manager needs to be concerned with the alternative cost - the cost of the lost opportunity. Management has to be able to make comparisons between the policy that should be chosen and the policy that should be rejected. Such comparisons require the ability to predict costs, rather than merely record costs.
Cost data are, of course, essential to the technique of cost prediction. However, the form in which much cost data are recorded limits accurate cost prediction to the field of comparable situations only. This limitation of accurate cost prediction may not be serious in industries where the production environment changes little from month to month or year to year. In harvesting, however, identical production situations are the exception rather than the rule. Unless the cost data are broken down and recorded as unit costs, and correlated with the factors that control their values, they are of little use in deciding between alternative procedures. Here, the approach to the problem of useful cost data is that of identification, isolation, and control of the factors affecting cost.
1.2 Basic Classification of Costs
Costs are divided into two types: variable costs, and fixed costs. Variable costs vary per unit of production. For example, they may be the cost per cubic meter of wood yarded, per cubic meter of dirt excavated, etc. Fixed costs, on the other hand, are incurred only once and as additional units of production are produced, the unit costs fall. Examples of fixed costs would be equipment move-in costs and road access costs.
1.3 Total Cost and Unit-Cost Formulas
As harvesting operations become more complicated and involve both fixed and variable costs, there usually is more than one way to accomplish a given task. It may be possible to change the quantity of one or both types of cost, and thus to arrive at a minimum total cost. Mathematically, the relationship existing between volume of production and costs can be expressed by the following equations:
Total cost = fixed cost + variable cost × output
In symbols using the first letters of the cost elements and N for the output or number of units of production, these simple formulas are
C = F + NV
UC = F/N + V
1.4 Breakeven Analysis
A breakeven analysis determines the point at which one method becomes superior to another method of accomplishing some task or objective. Breakeven analysis is a common and important part of cost control.
One illustration of a breakeven analysis would be to compare two methods of road construction for a road that involves a limited amount of cut-and-fill earthwork. It would be possible to do the earthwork by hand or by bulldozer. If the manual method were adopted, the fixed costs would be low or non-existent. Payment would be done on a daily basis and would call for direct supervision by a foreman. The cost would be calculated by estimating the time required and multiplying this time by the average wages of the men employed. The men could also be paid on a piece-work basis. Alternatively, this work could be done by a bulldozer which would have to be moved in from another site. Let us assume that the cost of the hand labor would be $0.60 per cubic meter and the bulldozer would cost $0.40 per cubic meter and would require $100 to move in from another site. The move-in cost for the bulldozer is a fixed cost, and is independent of the quantity of the earthwork handled. If the bulldozer is used, no economy will result unless the amount of earthwork is sufficient to carry the fixed cost plus the direct cost of the bulldozer operation.
Figure 1.1 Breakeven Example for Excavation.
If, on a set of coordinates, cost in dollars is plotted on the vertical axis and units of production on the horizontal axis, we can indicate fixed cost for any process by a horizontal line parallel to the x-axis. If variable cost per unit output is constant, then the total cost for any number of units of production will be the sum of the fixed cost and the variable cost multiplied by the number of units of production, or F + NV. If the cost data for two processes or methods, one of which has a higher variable cost, but lower fixed cost than the other are plotted on the same graph, the total cost lines will intersect at some point. At this point the levels of production and total cost are the same. This point is known as the "breakeven" point, since at this level one method is as economical as the other. Referring to Figure 1.1 the breakeven point at which quantity the bulldozer alternative and the manual labor alternative become equal is at 500 cubic meters. We could have found this same result algebraically by writing F + NV = F' + NV' where F and V are the fixed and variable costs for the manual method, and F' and V' are the corresponding values for the bulldozer method. Since all values are known except N, we can solve for N using the formula N = (F' - F) / (V - V')
1.5 Minimum Cost Analyses
A similar, but different problem is the determination of the point of minimum total cost. Instead of balancing two methods with different fixed and variable costs, the aim is to bring the sum of two costs to a minimum. We will assume a clearing crew of 20 men is clearing road right-of-way and the following facts are available:
1. Men are paid at the rate of $0.40 per hour.
2. Time is measured from the time of leaving camp to the time of return.
3. Total walking time per man is increasing at the rate of 15 minutes per day.
4. The cost to move the camp is $50.
If the camp is moved each day, no time is lost walking, but the camp cost is $50 per day. If the camp is not moved, on the second day 15 crew-minutes are lost or $2.00. On the third day, the total walking time has increased 30 minutes, the fourth day, 45 minutes, and so on. How often should the camp be moved assuming all other things are equal? We could derive an algebraic expression using the sum of an arithmetic series if we wanted to solve this problem a number of times, but for demonstration purposes we can simply calculate the average total camp cost. The average total camp cost is the sum of the average daily cost of walking time plus the average daily cost of moving camp. If we moved camp each day, then average daily cost of walking time would be zero and the cost of moving camp would be $50.00. If we moved the camp every other day, the cost of walking time is $2.00 lost the second day, or an average of $1.00 per day. The average daily cost of moving camp is $50 divided by 2 or $25.00. The average total camp cost is then $26.00. If we continued this process for various numbers of days the camp remains in location, we would obtain the results in Table 1.1.
TABLE 1.1 Average daily total camp cost as the sum of the cost of walking time plus the cost of moving camp.
Days camp remained in location | Average daily cost of walking time | Average daily cost of moving camp | Average total camp cost
1 | 0 | 50 | 50
2 | 1 | 25 | 26
3 | 2 | 16.67 | 18.67
4 | 3 | 12.5 | 15.5
5 | 4 | 10 | 14
6 | 5 | 8.33 | 13.33
7 | 6 | 7.14 | 13.14
8 | 7 | 6.25 | 13.25
9 | 8 | 5.56 | 13.56
10 | 9 | 5 | 14
We see the average daily cost of walking time increasing linearly and the average cost of moving camp decreasing as the number of days the camp remains in one location increases. The minimum cost is obtained for leaving the camp in location 7 days (Figure 1.2). This minimum cost point should only be used as a guideline as all other things are rarely equal. An important output of the analysis is the sensitivity of the total cost to deviations from the minimum cost point. In this example, the total cost changes slowly between 5 and 10 days. Often, other considerations which may be difficult to quantify will affect the decision. In Section 2, we discuss balancing road costs against skidding costs. Sometimes roads are spaced more closely together than that indicated by the point of minimum total cost if excess road construction capacity is available. In this case the goal may be to reduce the risk of disrupting skidding production because of poor weather or equipment availability. Alternatively, we may choose to space roads farther apart to reduce environmental impacts. Due to the usually flat nature of the total cost curve, the increase in total cost is often small over a wide range of road spacings.
Figure 1.2 Costs for Camp Location Example.

## Carpentry
Carpentry - Partitioning
Description | Tasks | Unit | Tradesman Hours | Labourer Hours
Wall linings
| 10mm Gib® standard plasterboard (fix only) | m2 | 0.2
| 10mm Gib® Braceline (fix only) | m2 | 0.22
| 13mm Gib® standard plasterboard (fix only) | m2 | 0.22
| 16mm Gib® standard plasterboard (fix only) | m2 | 0.26
| 19mm Gib® standard plasterboard (fix only) | m2 | 0.3
| Stopping of standard plasterboard | m2 | 0.25
| 4.75mm, 6mm hardboard | m2 | 0.3
| 12mm Pinex softboard | m2 | 0.18
| 4.5mm Hardiflex | m2 | 0.38
| 4.75mm plastic covered wallboard | m2 | 0.6
| 7.5mm, 9mm plywood | m2 | 0.5
| 13mm Pinex panels | m2 | 0.22
| 13mm Pinex acoustic tiles | m2 | 0.32
Extra values on linings, for
| Screw fixing | m2 | 0.45
| Glue fixing | m2 | 0.25
| PVC Jointers | m2 | 0.16
Wall strapping
| 50mm x 25mm at 300mm centres | m | 0.08
| 75mm x 25mm at 300mm centres | m | 0.08
| 50mm x 25mm at 600mm centres | m | 0.11
| 75mm x 25mm at 600mm centres | m | 0.11
| 50mm x 25mm at 600mm centres on concrete | m | 0.2
Ceiling linings
| 10mm Gib® standard plasterboard (fix only) | m2 | 0.22
| Stopping of standard plasterboard | m2 | 0.28
| 12mm Pinex softboard | m2 | 0.2
| 4.75mm, 6mm hardboard | m2 | 0.4
| 4.5mm fibre cement | m2 | 0.5
| 13mm Pinex panels | m2 | 0.3
| 13mm Pinex acoustic tiles | m2 | 0.35
| 4.75m Seratone | m2 | 0.38
Ceiling strapping
| 50mm x 25mm at 300mm centres | m | 0.08
| 75mm x 25mm at 300mm centres | m | 0.08
Task / Description | Slow | Ave | Fast | Units
Timber Studding | 5.9 | 6.2 | 6.8 | m/hr
Metalwork System (MF) Studding | 1.6 | 2.0 | 2.5 | m2/hr
Tape, Joint Sand and Top Coat Plasterboard | 1.1 | 1.5 | 2.1 | m2/hr
Skimming to Plasterboards | 5.5 | 6.1 | 6.7 | m2/hr
5mm Hardboard Paneling, excluding studding time | - | 3.2 | 3.6 | m2/hr
100mm Pine Paneling, excluding studding time | 0.8 | 1.1 | 1.4 | m2/hr
Quality Hardwood Paneling, excluding studding time | 0.3 | 0.5 | 0.6 | m2/hr
Fix 50mm Rocksil Insulation to cavities | - | 17.8 | 20.2 | m2/hr
Fix Timber Studding and Paramount Partitions | 2.6 | 3.0 | 3.4 | m2/hr
Fix Timber Studding and Demountable Partitions | 0.8 | 1.1 | 1.6 | m2/hr
Fix Timber Studding and Hills Duraboard Partitions | 3.0 | 3.5 | 3.9 | m2/hr
Fix Timber Studding and Gyproc Laminated Partitions | 2.2 | 2.6 | 2.9 | m2/hr
Stud Partitions, Butt Jointed, nailed | 5.9 | 7.3 | 9.1 | m/hr
Stud Partitions, Butt Jointed, screwed | 3.5 | 4.6 | 5.8 | m/hr
Stud Partitions, T&G Jointed, nailed | 2.9 | 3.6 | 4.8 | m/hr
Stud Partitions, T&G Jointed, screwed | 2.1 | 2.8 | 3.7 | m/hr
Stud Partitions, Fix Sole Plates | - | 11.1 | - | m/hr
Stud Partitions, Fix Noggins | - | 16.6 | - | m/hr
Stud Partitions, Drill 25-40mm Holes | - | 28.5 | - | no/hr
Fix Toilet Partition System, Separation panels | - | 0.8 | - | hrs/no
Fix Toilet Partition System, Wall Front Panels | - | 0.7 | - | hrs/no
Fix Toilet Partition System, Separation Front Panels | - | 0.6 | - | hrs/no
Fix Toilet Partition System, End Front Panels | - | 0.6 | - | hrs/no
Fix Toilet Partition System, Hang Door to Panel | - | 0.4 | - | hrs/no
Fix Toilet Partition System, Hand Door plugged to wall | - | 0.6 | - | hrs/no
Fix Toilet Partition System, Fix Head Rails | - | 0.1 | - | hrs/no
Carpentry-Exterior Trims
Description | Exterior Linings and Trim | Unit | Tradesman Hours | Labourer Hours
Weatherboards
Bevel back | 150mm x 25mm | m2 | 1
| 200mm x 25mm | m2 | 0.85
Vertical shiplap | 150mm x 25mm | m2 | 1.05
| 200mm x 25mm | m2 | 0.85
Rusticated | 150mm x 25mm | m2 | 0.65
| 200mm x 25mm | m2 | 0.5
PVC |  | m2 | 1
Fibre cement sheathing, including PVC jointers
| 4.5mm flat sheets | m2 | 0.35
| 6mm flat sheets | m2 | 0.35
| 7.5mm flat sheets | m2 | 0.45
| 7.5mm weatherboards | m2 | 0.9
Building paper and insulation
| Building paper | m2 | 0.08
| Sisalation | m2 | 0.15
| Batts between wall framing | m2 | 0.06
| Batts in ceiling | m2 | 0.09
Eaves soffit lining
| 4.5mm and 6mm fibre cement | m2 | 0.52
Deck sheathing
| 100mm x 25mm timber sheathing | m2 | 0.9
| 100mm x 25mm hardwood | m2 | 1.2
| 12mm fibre cement (screw fixed) | m2 | 1
Exterior finishings
| 150mm x 25mm, 200mm x 25mm fascia | m | 0.26
| 200mm x 40mm fascia | m | 0.33
| 50mm x 25mm, 75mm x 25mm, | m | 0.17
100mm x 25mm fascia
| 25mm x 25mm, 40mm x 25mm, | m | 0.15
50mm x 25mm beads, etc
Carpentry-Roof and Ceiling Framing
Description | Item | Unit | Tradesman Hours | Labourer Hours
Ceiling joist | 100mm x 50mm | m | 0.2
| 150mm x 50mm | m | 0.2
Ceiling dwang | 100mm x 50mm | m | 0.21
Ceiling strapping | 50mm x 25mm | m | 0.08
| 100mm x 25mm | m | 0.1
Rafter | 100mm x 50mm | m | 0.18
| 150mm x 50mm | m | 0.2
| 200mm x 50mm | m | 0.22
Collar tie | 150mm x 25mm | m | 0.17
Strut and brace | 100mm x 50mm | m | 0.12
| 100mm x 75mm | m | 0.22
Purlin | 75mm x 50mm | m | 0.12
| 100mm x 50mm | m | 0.15
| 150mm x 50mm | m | 0.17
| 200mm x 50mm | m | 0.2
Eaves framing | 75mm x 50mm | m | 0.18
| 100mm x 50mm | m | 0.2
Fascia | 100mm x 50mm | m | 0.17
| 150mm x 50mm | m | 0.2
Ridge board | 150mm x 25mm | m | 0.2
| 200mm x 25mm | m | 0.22
| 100mm x 50mm | m | 0.17
Valley board | 150mm x 25mm | m | 0.18
| 200mm x 25mm | m | 0.2
| 150mm x 50mm | m | 0.16
| 200mm x 50mm | m | 0.21
Beams and Lintels | 200mm x 50mm | m | 0.27
| 300mm x 75mm | m | 0.34
| 200mm x 100mm | m | 0.34
| 300mm x 100mm | m | 0.45
Posts | 100mm x 100mm | m | 0.28
Prefabricated roof trusses, erection only
| 6m span | No | 1.5
| 9m span | No | 2
| 12m span | No | 3
Carpentry-Bracing
Bracing | Description | Unit | Tradesman Hours | Labourer Hours
| Metal angle diagonal bracing | m | 0.12
| Plywood sheet bracing checked in flush | m2 | 0.9
| Plywood sheet bracing fixed over framing | m2 | 0.4
Carpentry-Wall Framing
Description | Wall Framing | Unit | Tradesman Hours | Labourer Hours
Plate | 75mm x 50mm | m | 0.12
| 100mm x 50mm | m | 0.13
| 150mm x 50mm | m | 0.15
Stud | 75mm x 50mm | m | 0.12
| 100mm x 50mm | m | 0.13
| 150mm x 50mm | m | 0.15
Jack stud | 75mm x 50mm | m | 0.13
| 100mm x 50mm | m | 0.13
| 150mm x 50mm | m | 0.24
Dwang | 75mm x 50mm | m | 0.13
| 100mm x 50mm | m | 0.17
| 150mm x 50mm | m | 0.24
Lintel | 100mm x 100mm | m | 0.26
| 150mm x 100mm | m | 0.36
| 200mm x 100mm | m | 0.46
| 250mm x 100mm | m | 0.5
| Metal studs 64mm | m | 0.12
Carpenty-Sub Floor Framing
Description | Sub Floor Framing | Unit | Tradesman Hours | Labourer Hours
Jack stud | 100mm x 100mm | m | 0.22
Bearer | 100mm x 75mm | m | 0.22
| 125mm x 100mm | m | 0.24
Joist | 150mm x 50mm | m | 0.2
| 200mm x 50mm | m | 0.21
| 250mm x 50mm | m | 0.22
| 300mm x 50mm | m | 0.22
Solid blocking | 100mm x 50mm | m | 0.17
| 150mm x 50mm | m | 0.23
| 200mm x 50mm | m | 0.25
| 300mm x 50mm | m | 0.32
Beam | 200mm x 50mm | m | 0.23
| 250mm x 50mm | m | 0.28
| 200mm x 100mm | m | 0.29
| 300mm x 100mm | m | 0.36
Carpentry-Flooring
Description | Item | Unit | Tradesman Hours | Labourer Hours
Tongued and grooved flooring
| 100mm x 25mm | m2 | 1.00-1.25
| 100mm x 25mm end matched | m2 | 0.75-1.00
Particle board
| 2400mm x 1200mm x 20mm sheet | m2 | 0.4
| 3600mm x 1200mm x 20mm sheet | m2 | 0.38
| 3600mm x 1800mm x 20mm sheet | m2 | 0.36
Plywood flooring
| 2400mm x 1200mm x 17.5mm sheet | m2 | 0.38
| 2400mm x 1200mm x 21mm sheet | m2 | 0.4
Carpentry-Water Proofing
Task / Description | Slow | Ave | Fast | Units
Asphalt coatings, horizontal surfaces | 3.5 | 4.2 | 5.8 | m2/hr
Asphalt coatings, vertical surfaces | 1.2 | 1.7 | 2.2 | m2/hr
Bituminous Brushed application, 2 coats | 4.8 | 5.0 | 6.3 | m2/hr
Bituminous Brushed application, 3 coats | 3.3 | 3.5 | 4.4 | m2/hr
Bituminous Sheets, horizontal surfaces | 3.8 | 4.0 | 4.8 | m2/hr
Bituminous Sheets, vertical surfaces | 3.3 | 3.5 | 4.2 | m2/hr
Polythene Sheets, horizontal surfaces | - | 20.0 | - | m2/hr
Bentonite Sheets, horizontal surfaces | 18.7 | 25.0 | 31.3 | m2/hr
Bentonite Sheets, vertical surfaces | 11.2 | 15.0 | 17.3 | m2/hr
Epoxy Based application, 1 coat | - | 75.0 | - | m2/hr
Epoxy Based application, 2 coat | - | 38.0 | - | m2/hr

## Interior Finishings
Interior Finishings
Doors & Frames Fixings
Description | Tasks | Unit | Tradesman Hours | Labourer Hours
Timber frame to suit door size
| 1980mm x 760mm, in stud wall | No | 1.5
Hollow core flush door, size
| 1980mm x 760mm on two hinges | No | 1.8
| 1980mm x 760mm on three hinges | No | 2
Solid core flush door, size
| 1980mm x 760mm on three hinges | No | 2
| 1980mm x 760mm on four hinges | No | 2.4
Panelled, framed and glazed door, size
| 1980mm x 760mm on two hinges | No | 2
| 1980mm x 760mm on three hinges | No | 2.4
Roller shutters
| Domestic shutter, 2100mm x 2400mm wide | No | 4
| Industrial shutter, 3000mm x 3000mm wide | No | 6
General finishes
Description | Item | Unit | Tradesman Hours | Labourer Hours
Interior Finishings
| Skirtings | m | 0.16
| Architraves | m | 0.18
| Cornices | m | 0.15
| Sill boards | m | 0.25
| Facings | m | 0.18
Task / Description | Slow | Ave | Fast | Units
Windows, Softwood, 3.0-7.0m2 | 0.6 | 0.4 | 0.3 | hrs/no
Windows, Softwood, 7.0-10.0m2 | 1.3 | 0.9 | 0.6 | hrs/no
Windows, Hardwood, 1.0-3.0m2 | 0.4 | 0.3 | - | hrs/no
Windows, Hardwood, 3.0-7.0m2 | 0.7 | 0.5 | 0.4 | hrs/no
Windows, Hardwood, 7.0-10.0m2 | 1.6 | 1.2 | 0.7 | hrs/no
Windows, Aluminum, 1.0-3.0m2 | 0.2 | 0.3 | - | hrs/no
Windows, Aluminum, 3.0-7.0m2 | 0.5 | 0.4 | 0.3 | hrs/no
Windows, Aluminum, 7.0-10.0m2 | 1.2 | 0.8 | 0.5 | hrs/no
Windows, Steel, 1.0-3.0m2 | 0.4 | 0.3 | 0.2 | hrs/no
Windows, Steel, 3.0-7.0m2 | 1.2 | 0.6 | 0.5 | hrs/no
Windows, Steel, 7.0-10.0m2 | 1.4 | 1.2 | 1.0 | hrs/no
Window Boards, nailed | - | 0.3 | 0.2 | hrs/m
Window Boards, screwed | - | 0.4 | 0.3 | hrs/m
Mouldings, Softwood, Nailed | - | 6.3 | 8.5 | m/hr
Mouldings, Softwood, Screwed | - | 4.6 | 5.6 | m/hr
Mouldings, Softwood, Gun Nailed | - | 8.2 | 11.1 | m/hr
Mouldings, Hardwood, Nailed | - | 3.3 | 5.5 | m/hr
Mouldings, Hardwood, Screwed | - | 2.4 | 3.7 | m/hr
Mouldings, Hardwood, Gun Nailed | - | 8.5 | 11.3 | m/hr
Skirting, Aluminum, Screwed 150-300mm centres | - | 7.6 | - | m/hr
Skirting, Aluminum, Screwed 300-450mm centres | - | 4.5 | - | m/hr
Skirting, Plastic, Adhesive Fixing | - | 8.6 | - | m/hr
Architrave Mouldings | 9.5 | 12.2 | 18.2 | m/hr
Architrave, Fix to Doors | - | 1.2 | - | hrs/door
Door Stop Mouldings | 10.1 | 16.9 | 25.0 | m/hr
Glazed Bead Mouldings | 15.5 | 18.6 | 20.4 | m/hr
Hanging Doors, Softwood, Single Pair Butts | 1.3 | 0.9 | 0.6 | hrs/no
Hanging Doors, Hardwood, Single Pair Butts | 1.9 | 1.2 | 0.9 | hrs/no
Cut Mortice to Receive Lock, Softwood | - | 0.2 | - | hrs/no
Cut Mortice to Receive Lock, Hardwood | - | 0.6 | - | hrs/no
Cut & Fix Formica Bath Panel | - | 0.4 | - | hrs/no
Kitchen Cupboards, Floor Units | - | 0.8 | 0.6 | hrs/no
Kitchen Cupboards, Wall Units | - | 0.7 | 0.5 | hrs/no
Kitchen Cupboards, Shelf Units | - | 0.8 | 0.7 | hrs/no
Staircase, pre-made, simple, straight flight | 1.9 | 1.5 | 1.1 | hrs/no
Staircase, pre-made, 2 straight flights, 1 landing | 3.7 | 2.9 | 2.6 | hrs/no
Staircase, pre-made, 2 straight flights, 2 landings | - | 6.3 | - | hrs/no
Staircase, Balustrades/Handrails, fix horizontal | 1.2 | 0.6 | 0.1 | hrs/no
Staircase, Balustrades/Handrails, fix raking | 0.9 | 0.5 | 0.3 | hrs/no
Staircase, Cut and Fix Newel to Walls | 0.9 | - | 0.2 | hrs/no
Windows, Softwood, 1.0-3.0m2 | 0.3 | 0.2 | - | hrs/no
Raised Flooring, metal system | - | 0.5 | - | m2/hr
Carcassing
Task / Description | Slow | Ave | Fast | Units
Windows, Timber Frames for Bricklaying | 1.1 | 0.5 | 0.1 | hrs/no
Windows, Drill, Screw & Plug extra over | 0.3 | 0.1 | - | hrs/no
Door Frames, Softwood, 1.0-3.0m2 | - | 0.2 | - | hrs/no
Door Frames, Softwood, 3.0-7.0m2 | 0.5 | 0.4 | - | hrs/no
Door Frames, Softwood, 7.0-10.0m2 | 1.2 | 0.8 | - | hrs/no
Door Frames, Hardwood, 1.0-3.0m2 | - | 0.3 | - | hrs/no
Door Frames, Hardwood, 3.0-7.0m2 | 0.6 | 0.3 | - | hrs/no
Door Frames, Hardwood, 7.0-10.0m2 | 1.4 | 1.0 | - | hrs/no
Erect Water Tank Platform | - | 2.3 | - | no/hr
Fix Studding For Bath | - | 0.1 | - | hrs/m
Cut Access Hatch | - | 0.3 | - | no/hr
Floor Joists, under 3m | 9.0 | 9.6 | 11.6 | no/hr
Floor Joists, 3.0-4.5m | 6.8 | 7.2 | 9.7 | no/hr
Floor Joists, 4.5-6.0m | 5.5 | 5.8 | 7.3 | no/hr
Ceiling Joists, under 3m | 12.8 | 14.0 | 14.7 | no/hr
Ceiling Joists, 3.0-4.5m | 10.8 | 12.1 | 12.6 | no/hr
Ceiling Joists, 4.5-6.0m | 9.6 | 10.8 | 11.1 | no/hr
Ceiling Joists, Notch to Beams | 20.0 | 25.0 | 28.5 | no/hr
Ceiling Joists, Pack Joist Ends | 20.1 | 23.8 | 26.3 | no/hr
Ceiling Joists, Nailing Joists together | - | 23.0 | - | m/hr
Ceiling Joists, Bolting Joists Together | - | 12.6 | - | m/hr
Floor Boards, Butt Jointed | - | 1.7 | - | m2/hr
Floor Boards, T&G Boards, under 75mm wide | - | 3.4 | - | m2/hr
Floor Boards, T&G Boards, 75-100mm wide | - | 3.8 | - | m2/hr
Floor Boards, T&G Boards, 100-125mm wide | - | 4.2 | - | m2/hr
Floor Boards, T&G Boards, 125-150mm wide | - | 5.5 | - | m2/hr
Plywood Sheeting, Butt Jointed, nailed | - | 9.1 | 10.2 | m2/hr
Plywood Sheeting, Butt Jointed, screwed | - | 4.1 | 4.8 | m2/hr
Plywood Sheeting, T&G Jointed, nailed | - | 8.3 | 9.1 | m2/hr
Plywood Sheeting, T&G Jointed, screwed | - | 4.0 | 4.6 | m2/hr
Chipboard Sheeting, Butt Jointed, nailed | - | 10.0 | 11.5 | m2/hr
Chipboard Sheeting, Butt Jointed, screwed | - | 5.1 | 5.8 | m2/hr
Chipboard Sheeting, T&G Jointed, nailed | - | 9.3 | 9.1 | m2/hr
Chipboard Sheeting, T&G Jointed, screwed | - | 5.5 | 5.9 | m2/hr
Commercial Kitchen
Task / Description | Slow | Ave | Fast | Units
Overall Installation for 100 persons or 50m2 | - | 3.0 | - | wks
Overall Installation for 500 persons or 150m2 | - | 5.0 | - | wks
Overall Installation for 1000 persons or 250m2 | - | 8.0 | - | wks
Install Ovens, friers and large mixers etc | - | 1.0 | - | mandays
Install Sinks, bain maries and washers etc | - | 2.0 | - | mandays
Suspended Ceilings
Task / Description | Slow | Ave | Fast | Units
Suspended Ceilings, office situations | - | 2.6 | 3.5 | m2/hr
Suspended Ceilings, First Fix | - | 0.7 | - | m2/hr
Suspended Ceilings, Second Fix | - | 1.2 | - | m2/hr
Hardware, Fix Only
Description | Item | Unit | Tradesman Hours | Labourer Hours
Hardware, Fix Only
| Lockset and furniture | Set | 0.8
| Surface mounted closer | No | 1.2
| Concealed closer | No | 1.6
Fixings
Description | Item | Unit | Tradesman Hours | Labourer Hours
Fixings
| Drill brick wall for 12mm dia. masonry anchor | No | 0.1
| Drill concrete wall for 12mm dia. masonry anchor | No | 0.13
| Drill timber for 6/12mm dia. bolt | No | 0.05
| Drill steel angle for 6/12mm dia. bolt | No | 0.13

## Joinery
Joinery
Staircases
Description | Item | Unit | Tradesman Hours | Labourer Hours
Staircases
| Timber staircase, comprising strings, treads, landing | m/rise | 8
supports and balustrades
| Handrail, 150mm x 50mm fixed to steel, including ramps | m | 0.45
and wreaths
Cupboards, Shelving
Description | Item | Unit | Tradesman Hours | Labourer Hours
Cupboards, Shelving
Cupboards, fabricate and fix
| Standard kitchen cupboard, 450mm wide x 900mm high | m | 6
| Shelving, 225mm x 25mm, fixed to framing | m | 0.17

## Roof and ceiling Framing
Flashings, Downpipes & Gutters
Description | Items | Unit | Tradesman Hours | Labourer Hours
Flashings, Downpipes, Gutters
Cover or apron flashing, sheet steel/aluminium
| 200mm-500mm girth | m | 0.45
| 500mm-800mm girth | m | 0.55
Downpipe with metal brackets at 900mm centres
| Sheet steel 100mm dia | m | 0.3
| PVC 100mm dia | m | 0.25
| Bend to steel or PVC | No | 0.1
Eaves gutter with metal brackets, straps at 900mm centres
| Standard sheet steel / aluminium | m | 0.35
| Standard PVC | m | 0.3
Box gutter, sheet steel/aluminium, with metal straps/
brackets at 900mm centres
| 600mm-800mm girth | m | 0.6
| 1000mm-1200mm girth | m | 0.7
Task / Description | Slow | Ave | Fast | Units
UPVC Downpipes, 75mm | - | 3.3 | - | m/hr
UPVC Guttering, 75mm | - | 3.1 | - | m/hr
UPVC RWP Fittings, 75mm | - | 3.1 | - | no/hr
Cast Iron Downpipes, 75mm | - | 2.1 | - | m/hr
Cast Iron Guttering, 75mm | - | 2.5 | - | m/hr
Cast Iron RWP Fittings, 75mm | - | 2.2 | - | no/hr
Aluminium Downpipes, 72mm | - | 2.5 | - | m/hr
Aluminium Guttering, 72mm | - | 2.9 | - | m/hr
Aluminium RWP Fittings, 72mm | - | 1.9 | - | no/hr
Timber Frames
Task / Description | Slow | Ave | Fast | Units
Roof Trusses | - | 1.3 | - | no/hr
Wall Plates | - | 2.7 | - | m/hr
Roof Rafters | - | 1.2 | - | m/hr
Ceiling Joists | - | 32.1 | - | m/hr
Roof Carcass, Common Rafters, under 3m | 18.2 | 20.0 | 21.7 | no/hr
Roof Carcass, Common Rafters, 3-6mm | 13.3 | 16.6 | 18.2 | no/hr
Roof Carcass, Common Rafters, over 6m | 14.1 | 15.6 | 16.1 | no/hr
Roof Carcass, Jack Rafters, under 3m | 18.8 | 20.1 | 21.7 | no/hr
Roof Carcass, Jack Rafters, 3-6mm | 10.4 | 16.1 | 16.6 | no/hr
Roof Carcass, Purlins, under 3m | 5.1 | 5.4 | 5.8 | no/hr
Roof Carcass, Purlins, 3-6mm | 4.3 | 4.8 | 5.1 | no/hr
Roof Carcass, Purlins, over 6m | 3.5 | 4.3 | 4.6 | no/hr
Roof Carcass, Binders, under 3m | 5.7 | 6.6 | 7.6 | no/hr
Roof Carcass, Binders, 3-6mm | 2.1 | 2.3 | 2.5 | no/hr
Roof Carcass, Binders, over 6m | 1.3 | 1.5 | 1.6 | no/hr
Roof Carcass, Hangers, under 3m | 8.2 | 9.0 | 9.6 | no/hr
Roof Carcass, Collars under 3m | 7.6 | 8.0 | 9.1 | no/hr
Roof Carcass, Collars 3-m | 6.5 | 7.4 | 8.3 | no/hr
Roof Carcass, Ridge Boards under 3m | 12.0 | 13.1 | 15.3 | no/hr
Roof Carcass, Cut Rafter Feet to line | 142.0 | 166.0 | 175.0 | no/hr
Roof Soffits, Softwood, nailed | - | 9.2 | - | m/hr
Roof Soffits, Softwood, screwed | - | 3.9 | - | m/hr
Roof Soffits Asbestos, under 300mm nailed | - | 9.1 | - | m/hr
Roof Soffits Asbestos, under 300mm screwed | - | 3.8 | - | m/hr
Roof Soffits, Asbestos, over 300mm nailed | - | 3.5 | - | m/hr
Roof Soffits, Asbestos, over 300mm screwed | - | 1.3 | - | m/hr
Roof Facia Panels, Softwood | 5.1 | 7.2 | 9.3 | m/hr
Roof Facia Panels, Asbestos | 1.3 | 2.5 | 3.9 | m/hr
Roof Facia Panel Studding, nailed | 7.3 | 8.1 | 9.0 | m/hr
Roof Facia Panel Studding, screwed | 4.6 | 5.2 | 5.8 | m/hr
Roof Facia Panel Studding, bolted to beams | 5.4 | 5.9 | 6.6 | m/hr
Roof Works, Fix Herringbone Strutting | - | 5.1 | - | m/hr
Roof Works, Fix Firing Strips | - | 25.0 | - | m/hr
Roof Works, Fix Drip/Tilt Filleting | - | 20.5 | - | m/hr
Slate and Tiling
Task / Description | Slow | Ave | Fast | Units
Slate Roofs, Welsh Slate 3-5mm | - | 18.0 | - | m2/day
Slate Roofs, Cumbrian Slate 8-11mm | - | 8.5 | - | m2/day
Slate Roofs, Asbestos Slates | - | 36.0 | - | m2/day
Tiled Roofs, Concrete Tiles | - | 52.0 | - | m2/day
Tiled Roofs, Clay Pan Tiles | - | 26.0 | - | m2/day
Sheeted Roofs
Task / Description | Slow | Ave | Fast | Units
PVC Sheeted Roofs, large areas | - | 50.0 | - | m2/day
PVC Sheeted Roofs, small areas | - | 40.0 | - | m2/day
Plastic Profiled Sheet Systems | - | 54.0 | - | m2/day
Rainwater Works
Description | Items | Unit | Tradesman Hours | Labourer Hours
Flashings, Downpipes, Gutters
Cover or apron flashing, sheet steel/aluminium
| 200mm-500mm girth | m | 0.45
| 500mm-800mm girth | m | 0.55
Downpipe with metal brackets at 900mm centres
| Sheet steel 100mm dia | m | 0.3
| PVC 100mm dia | m | 0.25
| Bend to steel or PVC | No | 0.1
Eaves gutter with metal brackets, straps at 900mm centres
| Standard sheet steel / aluminium | m | 0.35
| Standard PVC | m | 0.3
Box gutter, sheet steel/aluminium, with metal straps/
brackets at 900mm centres
| 600mm-800mm girth | m | 0.6
| 1000mm-1200mm girth | m | 0.7
Task / Description | Slow | Ave | Fast | Units
UPVC Downpipes, 75mm | - | 3.3 | - | m/hr
UPVC Guttering, 75mm | - | 3.1 | - | m/hr
UPVC RWP Fittings, 75mm | - | 3.1 | - | no/hr
Cast Iron Downpipes, 75mm | - | 2.1 | - | m/hr
Cast Iron Guttering, 75mm | - | 2.5 | - | m/hr
Cast Iron RWP Fittings, 75mm | - | 2.2 | - | no/hr
Aluminium Downpipes, 72mm | - | 2.5 | - | m/hr
Aluminium Guttering, 72mm | - | 2.9 | - | m/hr
Aluminium RWP Fittings, 72mm | - | 1.9 | - | no/hr
Metal Decking
Task / Description | Slow | Ave | Fast | Units
Metal Decking, large areas | - | 70.0 | - | m2/day
Metal Decking, small or complicated | - | 28.0 | - | m2/day
Titanium Sheeted Roofs | - | 9.5 | - | m2/day
Copper Roofs, flat work | - | 3.0 | - | m2/day
Copper Roofs, sloping work | - | 2.7 | - | m2/day
Zinc Roofs, flat work | - | 2.4 | - | m2/day
Zinc Roofs, sloping work | - | 2.1 | - | m2/day
Aluminium Roofs, flat work | - | 2.8 | - | m2/day
Aluminium Roofs, sloping work | - | 1.9 | - | m2/day
Lead Roofs, flat work | - | 2.5 | - | m2/day
Lead Roofs, sloping work | - | 2.1 | - | m2/day
Lead Roofs, dormer cheeks | - | 1.3 | - | m2/day
Lead Roofs, flat gutters | - | 88.0 | - | m/day
Lead Roofs, flat copings | - | 76.0 | - | m/day
Lead Roofs, stepped gutters | - | 3.5 | - | m/day
Lead Roofs, shaped copings | - | 3.3 | - | m/day
Lead Roofs, cover step flashings | - | 3.2 | - | m/day
Lead Roofs, rooflight flashings | - | 0.8 | - | no/day
Lead Roofs, domed roof coverings | - | 0.7 | - | m2/day
Flat and Layered Roofs
Task / Description | Slow | Ave | Fast | Units
Asphalt Roof in layers | - | 45.0 | - | m2/day
Fiber cement roofing sheets | - | 39.0 | - | m2/day
Felt Roofs, large areas | - | 52.0 | - | m2/day
Felt Roofs, small or complicated | - | 35.0 | - | m2/day
Felt Roofs, Gravel roof chippings | - | 1.4 | - | Tons/day
Underlay and Netting
Description | Item | Unit | Tradesman Hours | Labourer Hours
Underlay and Netting
| 50mm wire netting fixed to timber purlins | m2 | 0.05
| Building paper fixed to timber purlins | m2 | 0.04

## Lifts and Escalators
Escalators Installation
Task / Description | Slow | Ave | Fast | Units
Truss type, Overall Installation (excl arch finishes) | 14.0 | 12.0 | 11.0 | wks
Truss type, Manufacture, test and deliver | - | 60.0 | 48.0 | wks
Truss type, Phase A assemble truss , position/level | - | 1.0 | - | wks
Truss type, Stop-Work for surrounding finishes | 8.0 | 6.0 | 4.0 | wks
Truss type, Phase B decking and glazing etc | - | 5.0 | - | wks
Truss type, Phase C performance testing | - | 2.0 | - | wks
Truss type, Phase D full load testing | - | 2.0 | - | wks
Truss type, Phase E final test and inspection | - | 2.0 | - | wks
Lift Installation
Task / Description | Slow | Ave | Fast | Units
Hydraulic Lift, Install 2 to 3 storeys | - | 3.0 | - | wks/floor
Hydraulic Lift, Install 4 storeys and above | - | 2.0 | - | wks/floor
Hydraulic Lift, Testing allow 2 wks plus | - | 1.0 | - | day/floor
Standard Lift, Manufacture, test and deliver | - | 12.0 | - | wks
Non-Standard Lift, Manufacture, test and deliver | 75.0 | 65.0 | 52.0 | wks

## Suspended Ceilings
Description |  | Unit | Tradesman Hours | Labourer Hours
Grid Suspended Ceilings | Suspension Systems, suspended 600mm from
concrete soffit or steel purlins
| Fully concealed suspension system | m2 | 0.2
| Exposed grid system | m2 | 0.18
Linings
| 10mm plasterboard fixed to concealed suspension | m2 | 0.25
system
| Plasterboard tiles set into exposed grid system | m2 | 0.14

## Tiling
Task / Description | Slow | Ave | Fast | Units
Mosaic Tiling, 0.045x0.045m | - | 1.1 | 1.5 | no/hr
Clay, quarry Tiles, Window Cills, setout and level | - | 55.5 | - | m/hr
Clay, quarry Tiles, Window Cills, fix, grout and clean | - | 1.5 | - | m2/hr
Ceramic Tiles 150x150mm, Ledges/Upstands | 20.4 | 27.1 | 32.0 | no/hr
Ceramic Tiles 150x150mm, Areas under 1.5m2 per room | 0.9 | 1.0 | 1.2 | m2/hr
Ceramic Tiles 150x150mm, Areas of 1.5-2.5m2 per room | 1.4 | 1.6 | 1.9 | m2/hr
Ceramic Tiles 150x150mm, Areas over 2.5m2 per room | 1.5 | 1.7 | 2.1 | m2/hr
Ceramic Tiles 150x150mm, Extra Over for Cutting | - | 41.6 | - | no/hr
Ceramic Tiles 108x108mm, Ledges/Upstands | - | 62.5 | - | no/hr
Ceramic Tiles 108x108mm, Areas under 1.5m2 per room | 1.0 | 1.3 | 1.5 | m2/hr
Ceramic Tiles 108x108mm, Areas of 1.5-2.5m2 per room | 1.6 | 1.8 | 2.1 | m2/hr
Ceramic Tiles 108x108mm, Areas over 2.5m2 per room | 1.7 | 1.9 | 2.2 | m2/hr
Ceramic Tiles 108x108mm, Extra Over for Cutting | - | 125.0 | - | no/hr
Ceramic Tiles, Grouting Works | 2.2 | 2.5 | 2.6 | m2/hr

## Floor Coverings
Steel Frames
Task / Description | Slow | Ave | Fast | Units
Steel Frame and Roof Members | 3.4 | - | 4.6 | Tons/day
Wall Frame, Bow String Truss and Frame | - | 1.6 | - | Tons/day
Roof Frame, Curved Truss and Frame | - | 5.2 | - | Tons/day
Wall Frame, Glazed Frame and Atrium | - | 0.3 | - | Tons/day
Floor Finishes
Task / Description | Slow | Ave | Fast | Units
Granolithic Flooring | - | 3.1 | - | m2/hr
Terrazzo Flooring, in-situ | - | 3.6 | - | m2/hr
Terrazzo Flooring, pre-cast | - | 4.6 | 5.1 | m2/hr
Mosaic Tiling, 0.045x0.045m | - | 1.5 | 2.2 | m2/hr
Clay, quarry Tiles, small areas, much cutting | - | 0.8 | 1.1 | m2/hr
Clay, quarry Tiles, large areas, little cutting | - | 2.2 | 2.8 | m2/hr
Raised Floor System | - | 2.6 | - | m2/hr
Linolium/Thermo-Plastic Flooring | - | 3.1 | 5.0 | m2/hr
Thermo-Plastic Floor Tiles | - | 3.3 | 5.6 | m2/hr
Wood Block Flooring, lay blocks | - | 1.5 | 2.1 | m2/hr
Wood Block Flooring, sand and polish | - | 3.1 | - | m2/hr
Carpeting, Underlay & Gripper | - | 5.6 | 6.1 | m2/hr
Carpeting, Adhesive Fixing | - | 3.5 | 4.2 | m2/hr
Carpeting, Fully Fitted | - | 2.0 | 2.8 | m2/hr
Hardboard Sheeting Coverings, small areas | - | 3.7 | 4.1 | m2/hr
Hardboard Sheeting Coverings, large areas | - | 6.6 | 7.2 | m2/hr
Floor Sheeting Coverings, Lay Lino | - | 9.5 | 10.5 | m2/hr

## Glazing
Task / Description | Slow | Ave | Fast | Units
Vertical Glazed Lights, 6m x 2.5m | - | 14.5 | - | m2/day
Vertical Glazed Walls, large scale | - | 70.0 | - | m2/day
Clerestory Frame/Glazing, 3m x 4m | - | 28.0 | - | m2/day
Oriel Window Frame/Glazing, 4m x 2m | - | 35.0 | - | m2/day
Glazed Curtain Wall, First Fix | - | 1.2 | - | m2/hr
Glazed Curtain Wall, Second Fix | - | 1.1 | - | m2/hr
High Quality Glazed Curtain Walling | - | 25.0 | - | m2/day

## Wall Papering and Painting
Wall Papering
Task / Description | Slow | Ave | Fast | Units
Strip Existing Wallpaper (3 layers) & Prepare Walls | - | 5.0 | - | m2/hr
Fix Wallpaper and lining paper | - | 5.0 | - | m2/hr
Fix Vinyl and Washable paper | - | 4.2 | - | m2/hr
Fix Ceiling Lining Paper | - | 4.0 | - | m2/hr
Painting
Description |  | Unit | Tradesman Hours | Labourer Hours
Acrylic, prepare and apply two coats
| Walls | m2 | 0.2
| Ceilings and soffits | m2 | 0.25
| General timber/metal surfaces | m2 | 0.23
Enamel, prepare and apply two coats
| Walls | m2 | 0.3
| Ceilings and soffits | m2 | 0.32
| General timber/metal surfaces | m2 | 0.3
| Polyurethane, prepare and apply two coats to general | m2 | 0.18
timber surfaces
| Stain, prepare and apply two coats to general timber | m2 | 0.2
surfaces
Add 50% for painting/staining to joinery and windows
Paper hanging, prepare and hang on
| Ceilings | m2 | 0.34
| Walls | m2 | 0.3
Task / Description | Slow | Ave | Fast | Units
Prepare Walls | - | 14.2 | - | m2/hr
Prepare Doors | - | 12.5 | - | m2/hr
Prepare Door Frames | - | 25.0 | - | m/hr
Burn Off / Heat Strip Paintwork | - | 1.1 | - | m2/hr
Internal Timber, 1 coat primer before fixing, generally | - | 6.7 | - | m2/hr
Internal Timber, 1 coat primer before fixing, timber lengths | - | 20.0 | - | m/hr
Internal Timber, knot, 1 primer, stop, 1 undercoat, 1 gloss | - | 1.7 | 2.1 | m2/hr
Internal Timber, touchup primer, 1 undercoat, 1 coat gloss | - | 3.1 | 3.8 | m2/hr
Internal Timber, polyurethane varnish, 2 coats | - | 3.3 | - | m2/hr
Internal Timber, polyurethane varnish, 3 coats | - | 2.2 | - | m2/hr
Internal Timber, linseed oil to hardwood, 2 coats | - | 3.6 | - | m2/hr
External Timber, windows and frames | - | 2.4 | - | m2/hr
External Timber, knot, 1 primer, 2 undercoats, 1 coat gloss, | - | 1.5 | - | m2/hr
External Timber, touchup primer, 2 undercoats, 1 coat gloss, | - | 2.0 | - | m2/hr
External Timber, 2 coats wood preservative | - | 4.0 | - | m2/hr
External Timber, 3 coats polyurethane varnish | - | 2.0 | - | m2/hr
Internal Walls, 2 coats emulsion to plaster | - | 8.0 | - | m2/hr
Internal Walls, 2 coats emulsion to brick/blockwork | - | 6.0 | - | m2/hr
Internal Walls, 1 mist, 2 coats emulsion to plaster | - | 6.0 | - | m2/hr
Internal Walls, 1 mist, 2 coats emulsion to brick/blockwork | - | 4.5 | - | m2/hr
Internal Walls, 1 primer, 1 undercoat, 1 gloss to plaster | - | 2.3 | - | m2/hr
Internal Walls, undercoat to door frame | - | 20.0 | - | m/hr
Internal Walls, gloss to door frame | - | 16.5 | - | m/hr
Internal Walls, undercoat to door | - | 7.1 | - | m2/hr
Internal Walls, gloss to door | - | 6.2 | - | m2/hr
External Walls, 2 coats sandtex to render/concrete | - | 2.5 | - | m2/hr
External Walls, 2 coats sandtex to brick/blockwork | - | 2.0 | - | m2/hr
External Walls, 1 sealer, 2 emulsion to render/concrete | - | 2.0 | - | m2/hr
External Walls, 1 sealer, 2 emulsion to brick/blockwork | - | 1.7 | - | m2/hr
Floors, epoxy paint | - | 2.9 | - | m2/hr
Ceilings, emulsion paint, 2 coats | - | 6.1 | - | m2/hr
Ceilings, emulsion paint, 3 coats | - | 5.0 | - | m2/hr
Ceilings, textured paint | - | 4.2 | - | m2/hr
Ceilings, artex finish | - | 4.1 | - | m2/hr
Internal Steelwork, 1 primer, 1 undercoat, 1 gloss | 1.3 | 2.4 | - | m2/hr
External Steelwork, 1 primer, 2 undercoats, 1 gloss | 0.9 | 1.7 | - | m2/hr
Guttering Steelwork, 1 coat primer, 2 undercoats, 1 gloss | - | 2.5 | - | m/hr

## Plumbing
Sanitary Fixtures
Sanitary Fixtures | Description | Unit | Tradesman Hours | Labourer Hours
Fix only including brackets, fixings, etc
| Vanity basin | No | 1.7
| Wall basin | No | 1.75
| Bath, pressed steel | No | 1.4
| Bidet—excluding heater | No | 2
| W.C. suite | No | 2.35
W.C. pan floor mounted
| floor mounted | No | 1
| wall mounted | No | 4
| Cistern, wall type | No | 1
| Cleaner's sink | No | 1.8
| Kitchen sink | No | 1.5
| Laundry trough | No | 1
| Slop hopper | No | 5
| Urinal single stall | No | 3.5
| 1800mm long | No | 5
| 3000mm long | No | 6.5
Hot Water Units
Description |  | Unit | Tradesman Hours | Labourer Hours
Fix only, including connections to piping
| Instantaneous multi-point | No | 1.5
| 180 litre mains pressure, glass lined | No | 3
| Add for low pressure unit | No | 3
Cocks, Taps & Traps
Description |  | Unit | Tradesman Hours | Labourer Hours
Fix only including connections, diameter
Stop cock | 15mm to 25mm | No | 0.25
| 32mm | No | 0.35
| 40mm | No | 0.5
| 50mm | No | 0.75
Tap or faucet
| Basin combination set | Set | 0.5
| Laundry combination set | Set | 0.75
| Pillar tap | Set | 0.35
| Shower combination set | Set | 3
| Sink combination set | Set | 1.25
‘S’ or ‘P’ trap, copper or brass
| 40mm diameter | No | 0.25
| 50mm diameter | No | 0.3
‘S’ or ‘P’ trap, PVC
| 32mm diameter | No | 0.5
| 40mm diameter | No | 0.55
| 50mm diameter | No | 0.6
Soil, Waste and Vent Pipes
Description |  | Unit | Tradesman Hours | Labourer Hours
Constants include fixing to walls and testing.
Pipe constants exclude bends, junctions, etc. To include these in ‘per metre’ constant, allow one fitting for every 2 to 3 metres of pipe
Copper pipe, diameter | 32mm | m | 0.35
| 40mm | m | 0.4
| 50mm | m | 0.47
| 65mm | m | 0.53
| 80mm | m | 0.6
| 100mm | m | 0.68
| 150mm | m | 0.78
Bend, diameter | 32mm | No | 0.15
| 40mm | No | 0.18
| 50mm | No | 0.25
| 65mm | No | 0.3
| 80mm | No | 0.35
| 100mm | No | 0.45
| 150mm | No | 0.65
Junction, diameter | 32mm | No | 0.22
| 40mm | No | 0.26
| 50mm | No | 0.3
| 65mm | No | 0.35
| 80mm | No | 0.4
| 100mm | No | 0.5
| 150mm | No | 0.8
PVC pipe, diameter | 32mm | m | 0.25
| 40mm | m | 0.28
| 50mm | m | 0.3
| 65mm | m | 0.33
| 80mm | m | 0.38
| 100mm | m | 0.4
Bend, diameter | 32mm | No | 0.16
| 40mm | No | 0.18
| 50mm | No | 0.22
| 65mm | No | 0.27
| 80mm | No | 0.33
| 100mm | No | 0.42
Junction, diameter | 32mm | No | 0.18
| 40mm | No | 0.2
| 50mm | No | 0.24
| 65mm | No | 0.3
| 80mm | No | 0.35
| 100mm | No | 0.45
Water Pipes
Description |  | Unit | Tradesman Hours | Labourer Hours
Constants include fixing to walls and testing.
Pipe constants exclude bends, tees, etc. To include these in ‘per metre’ constant, allow one fitting for every 2 to 3 metres of pipe
Copper pipe, diameter | 15mm | m | 0.22
| 20mm | m | 0.24
| 25mm | m | 0.26
| 32mm | m | 0.3
| 40mm | m | 0.35
| 50mm | m | 0.4
| 65mm | m | 0.47
| 80mm | m | 0.55
| 100mm | m | 0.65
PVC pipe, diameter | 15mm | m | 0.13
| 20mm | m | 0.13
| 25mm | m | 0.16
| 32mm | m | 0.18
| 40mm | m | 0.2
| 50mm | m | 0.23
| 65mm | m | 0.26
| 80mm | m | 0.3
| 100mm | m | 0.35
Bend, diameter | 15mm | No | 0.1
| 20mm | No | 0.1
| 25mm | No | 0.1
| 32mm | No | 0.13
| 40mm | No | 0.15
| 50mm | No | 0.18
| 65mm | No | 0.2
| 80mm | No | 0.25
| 100mm | No | 0.33
Tee, diameter | 15mm | No | 0.14
| 20mm | No | 0.14
| 25mm | No | 0.14
| 32mm | No | 0.15
| 40mm | No | 0.18
| 50mm | No | 0.22
| 65mm | No | 0.24
| 80mm | No | 0.29
| 100mm | No | 0.38

## Masonry
Brickwork
Description |  | Unit | Tradesman Hours | Labourer Hours
Brickwork
Brickwork, stretcher bond
| Veneer walls, standard | 1000 bks | 16 | 8
| Facing, pointing and cleaning down | m2 | 0.2 | 0.06
Blockwork
Description |  | Unit | Tradesman Hours | Labourer Hours
Blockwork in walls, of hollow blocks
| 400mm x 200mm x 100mm | m2 | 0.43 | 0.22
| 400mm x 200mm x 150mm | m2 | 0.5 | 0.25
| 400mm x 200mm x 200mm | m2 | 0.56 | 0.28
| 400mm x 200mm x 200mm hollow block threaded over bar reinforcement | m2 | 0.96 | 0.28
| Pointing and cleaning down | m2 | 0.1 | 0.1
Labours and Filling
Fair raking cutting
| 100mm hollow block | m | 0.18 | 0.18
| 200mm hollow block | m | 0.28 | 0.28
Concrete filling to cores of hollow blocks
| 150mm hollow block | m2 | 0.45
| 200mm hollow block | m2 | 0.55
Lintel block, including filling
| 200mm wide x 200mm high x 200mm long | m | 0.4 | 0.14
| 200mm wide x 400mm high x 200mm long | m | 0.54 | 0.18
Task / Description | Slow | Ave | Fast | Units
Thermalite Blockwork, under 100mm thick | 1.8 | 2.5 | 3.2 | m2/hr
Thermalite Blockwork, under 100-150mm thick | 1.4 | 1.9 | 2.5 | m2/hr
Thermalite Blockwork, over 150mm thick | 1.2 | 1.6 | 2.1 | m2/hr
Lightweight Concrete Blockwork, under 100mm thick | 1.5 | 2.2 | 2.9 | m2/hr
Lightweight Concrete Blockwork, under 100-150mm thick | 1.4 | 1.9 | 2.1 | m2/hr
Lightweight Concrete Blockwork, over 150mm thick | 1.2 | 1.6 | 2.0 | m2/hr
Heavyweight Concrete Blockwork, under 100mm thick | 1.4 | 2.1 | 2.9 | m2/hr
Heavyweight Concrete Blockwork, under 100-150mm thick | 1.2 | 1.6 | 2.1 | m2/hr
Heavyweight Concrete Blockwork, over 150mm thick | 1.1 | 1.4 | 1.8 | m2/hr
Face Finish, Raked Out | - | 71.4 | - | m2/hr
Face Finish, Bag Rubbed | - | 29.4 | - | m2/hr
Face Finish, Flush Pointing | - | 17.6 | - | m2/hr
Plasterboard
Task / Description | Slow | Ave | Fast | Units
Boarding to Plaster dabs | 3.6 | 4.0 | 5.5 | m2/hr
Boarding to Stud-work/Metal Lathes | 4.0 | 5.0 | 6.7 | m2/hr
Boarding 12mm nailed to studding | - | 12.5 | - | m2/hr
Boarding 19mm nailed to studding | - | 16.5 | - | m2/hr
Tape, Jointing and Sanding | - | 0.1 | - | hrs/m
Plastering Production Rates
Description |  | Unit | Tradesman Hours | Labourer Hours
Solid Plaster
| Render for wall tiling, cement and sand in one coat 13mm thick | m2 | 0.2 | 0.1
Cement render, one coat 13mm thick on
| Walls | m2 | 0.25 | 0.11
| Soffits | m2 | 0.28 | 0.11
| Columns | m2 | 0.42 | 0.18
| Beams | m2 | 0.42 | 0.18
Hardwall plaster, two coats 16mm thick on
| Walls | m2 | 0.42 | 0.18
| Soffits | m2 | 0.5 | 0.2
| Columns | m2 | 0.55 | 0.25
| Beams | m2 | 0.55 | 0.25
| Skim coat hardwall plaster on soffits | m2 | 0.22 | 0.08
| Plaster cove | m | 0.15
| Plaster nosing | m | 0.15
Plastering Production Rates
Task / Description | Slow | Ave | Fast | Units
Browning (undercoat), Internal Walls under 2.5m high | 2.2 | 2.8 | 3.1 | m2/hr
Browning (undercoat), Internal Walls over 2.5m high | 2.1 | 2.6 | 2.8 | m2/hr
Browning (undercoat), Reveals and Columns less than 100mm wide | 9.9 | 10.0 | 10.1 | m2/hr
Browning (undercoat), Reveals and Columns 100-200mm wide | 5.2 | 5.4 | 6.4 | m2/hr
Browning (undercoat), Reveals and Columns 200-300mm wide | 3.3 | 3.6 | 3.9 | m2/hr
Covings | - | 5.0 | - | m/hr
Skimming (topcoat), Internal Walls under 2.5m high | 6.1 | 6.7 | 7.3 | m2/hr
Skimming (topcoat), Internal Walls over 2.5m high | 5.5 | 6.1 | 6.7 | m2/hr
Skimming (topcoat), Reveals and Columns less than 100mm wide | 12.6 | 13.8 | 15.4 | m2/hr
Skimming (topcoat), Reveals and Columns 100-200mm wide | 7.7 | 8.3 | 9.8 | m2/hr
Skimming (topcoat), Reveals and Columns 200-300mm wide | 4.5 | 5.0 | 5.5 | m2/hr
Plaster Board to Ceilings | 3.2 | 4.5 | 5.5 | m2/hr
Plastering Ceilings, 1 Bonding, 1 Skimming | 1.1 | 1.7 | 2.4 | m2/hr
Plastering Ceilings, Topcoat Skimming | 2.7 | 3.2 | 5.4 | m2/hr
Stonework
Task / Description | Slow | Ave | Fast | Units
Fix 0.5m2 Stones to Metal Support Frame | 5.6 | 7.0 | 7.8 | m2/day
Fix 0.5-0.75m2 Stones to Metal Support Frame | 7.2 | 9.0 | 10.1 | m2/day
Fix 0.75-1.0m2 Stones to Metal Support Frame | 6.9 | 8.7 | 9.7 | m2/day
Fix Complex Stonework to Metal Support Frame | - | 1.8 | - | m2/day
Fix Curved Stone Cladding | 6.9 | 8.0 | 9.2 | m2/day
Fix Stone Edge Beams/Window Reveals | - | 2.3 | 3.2 | m2/day
Fix Stone Soffits | - | 4.0 | - | m2/day
Stone Floors | 6.9 | 10.4 | 12.2 | m2/day
Granite Wall Panels, First Fix | - | 1.3 | - | m2/hr
Granite Wall Panels, Second Fix | - | 1.1 | - | m2/hr

## Tower cranes
Task / Description | Slow | Ave | Fast | Units
Erect and Setup 50m gib | - | 11.0 | 7.5 | days
Dismantle 50m gib | - | 10.0 | - | days
Lifting, Reinforcement Bins and Cages, 1st 15m lift | - | 3.2 | - | mins/lift
Lifting, Reinforcement Bins and Cages, above 1st 15m lift | - | 0.5 | - | mins/15m
Lifting, Crane Tracking Time | - | 3.3 | - | seconds/m